## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED BHULKI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13223 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Bhulki water supply scheme, TW no III and IV under Northern Mechanical Division-II, PHE Dte. APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000813/2023-2024 | 2392/NMD-II | 09/08/2023 | 08/09/2023 | B.B CONCERNED | 20.8 | 17.28 | 83.06 | 40
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BHULKI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13223 | Augmentation | Execution of different works related to AUG. of BHULKI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000882/2022-2023 | 1984/CD | 27/03/2023 | 21/01/2024 | SUJIT KUMAR SAHA | 251.25 | 99.66 | 39.67 | 34
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BHULKI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13223 | Augmentation | Execution of different works related to CHHOTO GAROLJHORA area BHULKI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000413/2023-2024 | 1316/CD | 24/11/2023 | 23/01/2024 | HIRAK CONSTRUCTION | 4.32 | 0 | 0 | 0
4 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED BHULKI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13223 | Augmentation | Hiring of Inspection Vehicle for Office of the Assistant Engineer, Coochbehar Mechanical Sub-Division , I.C.W JJM Works under Northern Mechanical Division -II , P.H.E Dte. |  | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000380/2024-2025 | 2080/CMSD | 22/07/2024 | 22/09/2024 | DIPAK SARKAR | 0.69 | 0 | 0 | 100
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BHULKI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13223 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED BHULKI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13223 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO NIGAMNAGAR PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000620/2024-2025 | 2321/CD | 23/12/2024 | 21/02/2025 | TAPAN CHANDA | 96.52 | 0 | 0 | 0
7 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED BHULKI PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13223 | Augmentation | Charges for new service connection at Aug of Bhulki PWSS, P/H-III under Coochbehar Dist. |  |  | BILL/00602/2025-2026 |  | 28/05/2025 | 28/05/2025 | WBSEDCL | 8.76 | 0 | 0 | 0
Total | [13 empty] | 20171.64 | 116.94 | 0.58