## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED KHATTIMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13224 | Augmentation | Execution of different works related to AUG. of KHATTIMARI ZONE-I PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1403/1-5/NBC-1; Dt.: 31-03-23 | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000685/2022-2023 | 2022/CD | 31/03/2023 | 28/08/2023 | ASHIM KUMAR CHAKRABORTY | 285.99 | 0 | 0 | 1
2 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED KHATTIMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13224 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for AGUMENTATION OF KHATTIMARI T.W No.-I and II of Zone-I under NMD-II,PHE.Dte,Alipurduar. |  |  | ORD/001074/2023-2024 | 2764/NMD-II | 04/10/2023 | 03/11/2023 | A.S. ENTERPRISE | 20.76 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED KHATTIMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13224 | Augmentation | Preparation of DPR for Augmentation of Khattimari Piped Water Supply Scheme under Cooch Behar Sadar Sub-division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000303/2021-2022 | 1018/CD | 10/01/2022 | 30/01/2022 | RADIANT | 3.31 | 0 | 0 | 1
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED KHATTIMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13224 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000101/2023-2024 | 198/CD | 27/04/2023 | 27/04/2023 | Resource Division | 19.23 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED KHATTIMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13224 | Augmentation | Execution of different works related to KHATTIMARI (ZONE-II) PWSS under JAL JEEVAN MISSION |  |  | ORD/000063/2024-2025 | 1310/CD | 16/07/2024 | 14/10/2024 | AMBITIOUS ENTERPRISE | 0 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED KHATTIMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13224 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED KHATTIMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13224 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000074/2025-2026 | 789/CD | 23/05/2025 | 21/08/2025 | SHREE RANI SATI ENTERPRISE | 69.41 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED KHATTIMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13224 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000079/2025-2026 | 651/CD | 05/05/2025 | 03/08/2025 | GOUTAM KUMAR DAS | 91.22 | 0 | 0 | 0
Total | [13 empty] | 20279.21 | 0 | 0