## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED KUCHLIBARI ZONE-II PWSS | SM/13225 | Augmentation | Providing FHTC & Laying P/Line at KUCHLIBARI ZONE I & II PWSS under Cooch Behar Division, PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000022/2022-2023 | 38/CD | 07/04/2022 | 22/05/2022 | RAJIB CHAKRABORTY | 34.81 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED KUCHLIBARI ZONE-II PWSS | SM/13225 | Augmentation | Providing functional house hold tap connection (unmetered) 145 nos. in Kuchlibari Zone-II Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. Part-D | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000049/2022-2023 | 10/MTB | 11/04/2022 | 26/04/2022 | RAJIB CHAKRABORTY | 5.04 | 0 | 0 | 1
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED KUCHLIBARI ZONE-II PWSS | SM/13225 | Augmentation | Providing functional house hold tap connection (unmetered) 145 nos. in Kuchlibari Zone-I Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. Part-D | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000050/2022-2023 | 14/MTB | 11/04/2022 | 26/04/2022 | RAJIB CHAKRABORTY | 5.04 | 0 | 0 | 1
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED KUCHLIBARI ZONE-II PWSS | SM/13225 | Augmentation | Providing FHTC and Laying of Pipe line of KUCHLIBARI ZONE ¿ II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000395/2022-2023 | 1036/CD | 29/09/2022 | 28/11/2022 | RAJIB CHAKRABORTY | 36.96 | 0 | 0 | 1
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED KUCHLIBARI ZONE-II PWSS | SM/13225 | Augmentation | Providing FHTC & Contn of HWS B/wall Gate & Misc other allied works at KUCHLIBARI Z-II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000337/2022-2023 | 990/CD | 29/09/2022 | 29/10/2022 | RAJIB CHAKRABORTY | 23.91 | 0 | 0 | 1
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED KUCHLIBARI ZONE-II PWSS | SM/13225 | Augmentation | Preparation of DPR for Augmentation of KUCHLIBARI (Zone-II) Piped Water Supply Scheme under MATHABHANGA Sub-Division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000164/2022-2023 | 623/CD | 16/08/2022 | 05/09/2022 | RADIANT | 3.08 | 0 | 0 | 1
7 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED KUCHLIBARI ZONE-II PWSS | SM/13225 | Augmentation | QUOTATION FOR NSC AT KUCHLBARI ZONE-II, TW NO II |  |  | BILL/01731/2023-2024 | BP-2023-24-312 | 27/09/2023 | 27/09/2023 | WBSEDCL | 5.76 | 0 | 0 | 0
8 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED KUCHLIBARI ZONE-II PWSS | SM/13225 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for KUCHLIBARI TW NO.II OF ZONE-I,T/W NO.IV Water Supply Scheme under NMDII, PHE. Dte, APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000705/2023-2024 | 2061/NMD-II | 26/07/2023 | 25/08/2023 | RMD TRADING | 21.17 | 0 | 0 | 50
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED KUCHLIBARI ZONE-II PWSS | SM/13225 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO Kuchlibari Zone-I, KUCHLIBARI ZONE-II AND ANDARAN KUCHLIBARI PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000527/2024-2025 | 2290/CD | 23/12/2024 | 21/02/2025 | M/S BADAL CH SAHA | 94.71 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED KUCHLIBARI ZONE-II PWSS | SM/13225 | Augmentation | Execution of different works related to KUCHLIBARI Z 2 PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1013/1-5/NBC-1; Dt.: 24-01-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000493/2022-2023 | 1558/CD | 24/01/2023 | 29/04/2025 | MANABENDRA DE | 189.39 | 0 | 0 | 60
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED KUCHLIBARI ZONE-II PWSS | SM/13225 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
12 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED KUCHLIBARI ZONE-II PWSS | SM/13225 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO (within NAGAR CHANGRABANDA KUCHLIBARI ZONE-II & UCHAL PUKHARI ZONE-I area) ANDARAN NIJTARAF PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000680/2024-2025 | 2317/CD | 23/12/2024 | 21/06/2025 | DAS ENTERPRISE | 37.3 | 0 | 0 | 50
13 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED KUCHLIBARI ZONE-II PWSS | SM/13225 | Augmentation | Execution of different works related to KUCHLIBARI Z II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000064/2024-2025 | 1322/CD | 19/07/2024 | 18/11/2025 | M/S PALIT ENTERPRISE | 20.22 | 0 | 0 | 30
Total | [13 empty] | 20266.68 | 0 | 0