## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SOULMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13226 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Dinhata-I Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000825/2022-2023 | 2045/CD | 31/03/2023 | 31/05/2023 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 0
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SOULMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13226 | Augmentation | Preparation of DPR for Augmentation of SOULMARI (Zone-II) Piped Water Supply Scheme under COOCH BEHAR SADAR Sub-Division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCHBEHAR DIVISION | ORD/000168/2022-2023 | 627/CD | 16/08/2022 | 05/09/2022 | RADIANT | 2.69 | 2.69 | 100 | 1
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SOULMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13226 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000103/2023-2024 | 200/CD | 27/04/2023 | 27/04/2023 | Resource Division | 19.66 | 0 | 0 | 0
4 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED SOULMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13226 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Soulmari (Dinhata-II) water supply scheme, TW no. I and II of Zone-Iand II under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000827/2023-2024 | 2397/NMD-II | 09/08/2023 | 08/09/2023 | DAS ENTERPRISE | 41.51 | 0 | 0 | 50
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SOULMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13226 | Augmentation | Execution of different works related to BARO SOULMARI PWSS under JAL JEEVAN MISSION MTB | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000556/2023-2024 | 654/CD | 11/03/2024 | 10/05/2024 | LIMRA CONSTRUCTION AND INDUSTRIAL DEVELOPMENT | 51.5 | 15.66 | 30.41 | 30
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SOULMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13226 | Augmentation | Execution of different works related to AUG. SOULMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000055/2024-2025 | 1269/CD | 02/07/2024 | 30/09/2024 | M/S A. B. ENTERPRISE | 39.89 | 26 | 65.19 | 30
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SOULMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13226 | Augmentation | Execution of different works related to AUG. SOULMARI PWSS under JAL JEEVAN MISSION |  |  | ORD/000036/2024-2025 | 1137/CD | 14/06/2024 | 13/08/2024 | M/S A. B. ENTERPRISE | 0 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SOULMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13226 | Augmentation | HIRING VEWHICLE FOR AE HQ |  |  | BILL/00596/2024-2025 | BP-231 | 01/08/2024 | 01/08/2024 | BHAGWATI BHUJEL | 0.77 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SOULMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13226 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000253/2025-2026 | 762/CD | 17/05/2025 | 15/08/2025 | MS BIDYUT SARKAR | 96.92 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SOULMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13226 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000264/2025-2026 | 770/CD | 17/05/2025 | 13/11/2025 | KARTICK CH SEAL | 32.3 | 0 | 0 | 80
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SOULMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13226 | Augmentation | Execution of different works related to SOULMARI Z 1 PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1129/1-5/NBC-1; Dt.: 13-02-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000623/2022-2023 | 1691/CD | 13/02/2023 | 04/03/2025 | SWAPAN KUMAR ROY | 277.32 | 220.81 | 79.62 | 50
12 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SOULMARI ZONE-I PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN DINHATA-II BLOCK WITHIN COOCH BEHAR DISTRICT UNDER COOCH BEHAR DIVISION, P.H.E. DTE. | SM/13226 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000286/2025-2026 | 795/CD | 23/05/2025 | 19/11/2025 | NORTH BENGAL CONSTRUCTION CO | 37.91 | 0 | 0 | 30
Total | [13 empty] | 601.45 | 266.14 | 44.25