## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF UCHAL PUKHARI ZONE-I PUBLICWATER SUPPLY SCHEME. | SM/13228 | Augmentation | Shifting pipeline due to widening & strengthening of Jamaldah Ranirhat via Uchalpukuri road from 0.00 km to 12.70 km by COB Highway Divn.-III under Cooch Behar Division. PHE Dte. Part D | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000094/2021-2022 | 291/CD | 13/08/2021 | 27/09/2021 | MS SSB CONSTRUCTION CO | 23.74 | 18.19 | 76.64 | 1
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF UCHAL PUKHARI ZONE-I PUBLICWATER SUPPLY SCHEME. | SM/13228 | Augmentation | Providing functional house hold tap connection within command area of Uchalpukuri Zone-I Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000154/2022-2023 | 210/MTB | 26/07/2022 | 10/08/2022 | BISWAJIT GUHA | 4.79 | 4.79 | 100 | 1
3 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF UCHAL PUKHARI ZONE-I PUBLICWATER SUPPLY SCHEME. | SM/13228 | Augmentation | Quotation for burnt meter at Uchalpukhari Z-I ,P/H No-I Application No- 4002935563 |  |  | BILL/00005/2022-2023 |  | 23/11/2022 | 23/11/2022 | WBSEDCL | 0.09 | 0 | 0 | 0
4 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF UCHAL PUKHARI ZONE-I PUBLICWATER SUPPLY SCHEME. | SM/13228 | Augmentation | Quotation for brunt meter at UCHAL PUKHARI Z-I,P/H no. I, Application no. 4002935563 |  |  | VCH/001472/2022-2023 | BP-95/22-23 | 28/11/2022 | 28/11/2022 | WBSEDCL | 0.09 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF UCHAL PUKHARI ZONE-I PUBLICWATER SUPPLY SCHEME. | SM/13228 | Augmentation | Shifting pipeline due to widening & strengthening of Jamaldah Ranirhat via Uchalpukuri Z-I road from 0.00 km to 12.70 km by COB Highway Divn.-III under Cooch Behar Division. PHE Dte. Part I | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000095/2021-2022 | 307/CD | 13/08/2021 | 27/09/2021 | MS SSB CONSTRUCTION CO | 23.9 | 18.5 | 77.4 | 1
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF UCHAL PUKHARI ZONE-I PUBLICWATER SUPPLY SCHEME. | SM/13228 | Augmentation | Providing FHTC & other allied works at UCHALPUKURI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000357/2022-2023 | 1010/ CD | 29/09/2022 | 29/10/2022 | TISTA LABOUR CO-OP CONT AND CONST SOCIETY LTD | 9.98 | 5.5 | 55.08 | 56
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF UCHAL PUKHARI ZONE-I PUBLICWATER SUPPLY SCHEME. | SM/13228 | Augmentation | Preparation of DPR for Augmentation of Uchal Pukri Piped Water Supply Scheme under Mathabhanga Sub-division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000292/2021-2022 | 1007/CD | 10/01/2022 | 30/01/2022 | RADIANT | 3.31 | 3.31 | 100 | 1
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF UCHAL PUKHARI ZONE-I PUBLICWATER SUPPLY SCHEME. | SM/13228 | Augmentation | Execution of different works related to UCHALPUKURI ZONE -I PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1017/1-5/NBC-1; Dt.: 24-01-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000489/2022-2023 | 1554/CD | 24/01/2023 | 23/06/2023 | PALLAB BHAWAL | 494.3 | 403.2 | 81.57 | 43
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF UCHAL PUKHARI ZONE-I PUBLICWATER SUPPLY SCHEME. | SM/13228 | Augmentation | HIRING VEHICLE FOR EE/CD |  |  | BILL/00482/2024-2025 | BP-206 | 31/07/2024 | 31/07/2024 | SWAPAN KR.SARKAR | 0.34 | 0 | 0 | 0
10 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF UCHAL PUKHARI ZONE-I PUBLICWATER SUPPLY SCHEME. | SM/13228 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Uchalpukhari water supply scheme, TW no. III of Zone-I and II under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000828/2023-2024 | 2396/NMD-II | 09/08/2023 | 02/09/2025 | SARKAR ELECTRIC | 20.8 | 17.21 | 82.74 | 80
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF UCHAL PUKHARI ZONE-I PUBLICWATER SUPPLY SCHEME. | SM/13228 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
12 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF UCHAL PUKHARI ZONE-I PUBLICWATER SUPPLY SCHEME. | SM/13228 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO (within NAGAR CHANGRABANDA KUCHLIBARI ZONE-II & UCHAL PUKHARI ZONE-I area) ANDARAN NIJTARAF PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000680/2024-2025 | 2317/CD | 23/12/2024 | 16/02/2026 | DAS ENTERPRISE | 37.3 | 0 | 0 | 50
13 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF UCHAL PUKHARI ZONE-I PUBLICWATER SUPPLY SCHEME. | SM/13228 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO UCHALPUKURI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000553/2024-2025 | 2238/CD | 23/12/2024 | 10/10/2025 | MAHARAJA CONSTRUCTION CO. | 94.56 | 0 | 0 | 30
14 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF UCHAL PUKHARI ZONE-I PUBLICWATER SUPPLY SCHEME. | SM/13228 | Augmentation | ELECTRIC QUOTATION BILL FOR NSC AT UCHAL PUKHRI PWSS ZONE-I TW III. |  |  | BILL/02034/2024-2025 | BP-455/24-25 | 09/01/2025 | 09/01/2025 | WBSEDCL | 5.71 | 0 | 0 | 0
15 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF UCHAL PUKHARI ZONE-I PUBLICWATER SUPPLY SCHEME. | SM/13228 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO (within UCHAL PUKHARI ZONE-I, PURBBA DHULIA BALDIHATI & SHIKARPUR area) NIJTARAF PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000593/2024-2025 | 2277/CD | 23/12/2024 | 16/06/2026 | M/S SURAJIT MAJUMDER | 47.03 | 3.03 | 6.45 | 30
16 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF UCHAL PUKHARI ZONE-I PUBLICWATER SUPPLY SCHEME. | SM/13228 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000077/2025-2026 | 650/CD | 05/05/2025 | 29/07/2026 | SUPER -TECH ENGINEERS'CO-OPERATIVE SOCIETY LIMITED | 69.03 | 0 | 0 | 60
Total | [13 empty] | 20624.26 | 473.73 | 2.3