## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground Water Based Chilkirhat PWSS (Cooch Behar-I Block) under Cooch Behar Division, P.H.E .Dte. | SM/13229 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT CHILKIRHAT (AUG) PH NO-I |  |  | BILL/00157/2023-2024 | BP-2023-24-115 | 18/05/2023 |  | WBSEDCL | 1.06 | 0 | 0 | 0
2 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground Water Based Chilkirhat PWSS (Cooch Behar-I Block) under Cooch Behar Division, P.H.E .Dte. | SM/13229 | Augmentation | New service connection for CHILKIRHAT(AUG) PWSS, PH-II |  |  | BILL/02065/2023-2024 | BP-2023-24-437 | 05/12/2023 |  | WBSEDCL | 9.94 | 0 | 0 | 0
3 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground Water Based Chilkirhat PWSS (Cooch Behar-I Block) under Cooch Behar Division, P.H.E .Dte. | SM/13229 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Chilkirhat Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000889/2023-2024 | 2463/NMD-II | 11/08/2023 | 10/09/2023 | SUDIP DUTTA | 18.42 | 0 | 0 | 60
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Chilkirhat PWSS (Cooch Behar-I Block) under Cooch Behar Division, P.H.E .Dte. | SM/13229 | Augmentation | Execution of different works related to CHILKIRHAT PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1175/1-5/NBC-1; Dt.: 24-02-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000684/2022-2023 | 1615/CD | 03/02/2023 | 03/07/2023 | S N POLYMERS PVT LTD | 375.65 | 179.9 | 47.89 | 30
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Chilkirhat PWSS (Cooch Behar-I Block) under Cooch Behar Division, P.H.E .Dte. | SM/13229 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
Total | [13 empty] | 20194.35 | 179.9 | 0.89