## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Dakshin Basrajbala Zone-I PWSS (HALDIBARI Block) | SM/13230 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000087/2023-2024 | 202/CD | 27/04/2023 | 27/04/2023 | Resource Division | 16.01 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Dakshin Basrajbala Zone-I PWSS (HALDIBARI Block) | SM/13230 | Augmentation | Execution of different works related to DAKSHIN BASARAJBALA ZONE I PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1118/1-5/NBC-1; Dt.: 13-02-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000570/2022-2023 | 1686/CD | 13/02/2023 | 13/07/2023 | S G CONSTRUCTION | 214.41 | 193.33 | 90.17 | 95
3 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground Water Based Dakshin Basrajbala Zone-I PWSS (HALDIBARI Block) | SM/13230 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Dakshin Basrajbala Water Supply Scheme TW No.-I and II of Zone-I under NMD-II,PHE.Dte,Apd. | Assistant Engineer,Cooch-Behar Mechanical Sub-Division, | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000891/2023-2024 | 2479/NMD-II | 11/08/2023 | 10/09/2023 | KARMAKAR CONSTRUCTION | 21.69 | 0 | 0 | 100
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Dakshin Basrajbala Zone-I PWSS (HALDIBARI Block) | SM/13230 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Dakshin Basrajbala Zone-I PWSS (HALDIBARI Block) | SM/13230 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DAKSHIN BASRAJBALA Zone- I & II PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000657/2024-2025 | 86/CD | 17/01/2025 | 18/11/2025 | SHRI ANNAPURNA DISTRIBUTORS | 65.57 | 0 | 0 | 40
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Dakshin Basrajbala Zone-I PWSS (HALDIBARI Block) | SM/13230 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000284/2025-2026 | 793/CD | 23/05/2025 | 21/08/2025 | PALLAB BHAWAL | 30.52 | 0 | 0 | 0
Total | [13 empty] | 20137.5 | 193.33 | 0.96