## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Dakshin Basrajbala Zone-I PWSS (HALDIBARI Block) | SM/13230 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000087/2023-2024 | 202/CD | 27/04/2023 |  | Resource Division | 16.01 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Dakshin Basrajbala Zone-I PWSS (HALDIBARI Block) | SM/13230 | Augmentation | Execution of different works related to DAKSHIN BASARAJBALA ZONE I PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1118/1-5/NBC-1; Dt.: 13-02-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000570/2022-2023 | 1686/CD | 13/02/2023 | 13/07/2023 | S G CONSTRUCTION | 214.41 | 109.2 | 50.93 | 95
3 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground Water Based Dakshin Basrajbala Zone-I PWSS (HALDIBARI Block) | SM/13230 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Dakshin Basrajbala Water Supply Scheme TW No.-I and II of Zone-I under NMD-II,PHE.Dte,Apd. | Assistant Engineer,Cooch-Behar Mechanical Sub-Division, | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000891/2023-2024 | 2479/NMD-II | 11/08/2023 | 10/09/2023 | KARMAKAR CONSTRUCTION | 21.69 | 0 | 0 | 50
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Dakshin Basrajbala Zone-I PWSS (HALDIBARI Block) | SM/13230 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
Total | [13 empty] | 20041.4 | 109.2 | 0.54