## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata-I | Coochbehar Division | BAISGURI KHANDA PIPED WATER SUPPLY SCHEME | SM/13284 | New | Material Requisition To Resource Division |  |  | RTOR000068/2023-2024 | 176/CD | 27/04/2023 | 27/04/2023 | Resource Division | 25.78 | 0 | 0 | 0
2 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | BAISGURI KHANDA PIPED WATER SUPPLY SCHEME | SM/13284 | New | New service connection at Baisguri pwss, P/H-I |  |  | BILL/02144/2023-2024 | BP-2023-24-468 | 07/12/2023 | 07/12/2023 | WBSEDCL | 8.19 | 0 | 0 | 0
3 | COOCHBEHAR | Dinhata-I | Coochbehar Division | BAISGURI KHANDA PIPED WATER SUPPLY SCHEME | SM/13284 | New | Execution of different works related to BAISGURI KHANDA PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1242/1-5/NBC-1; Dt.: 02-03-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000552/2022-2023 | 1774/CD | 02/03/2023 | 30/07/2023 | MS BIDYUT SARKAR | 534.3 | 0 | 0 | 37
4 | COOCHBEHAR | Dinhata-I | Coochbehar Division | BAISGURI KHANDA PIPED WATER SUPPLY SCHEME | SM/13284 | New | Execution of different works related to BAISGURI KHANDA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000021/2024-2025 | 1129/CD | 14/06/2024 | 13/08/2024 | MS BIDYUT SARKAR | 95.98 | 0 | 0 | 30
5 | COOCHBEHAR | Dinhata-I | Coochbehar Division | BAISGURI KHANDA PIPED WATER SUPPLY SCHEME | SM/13284 | New | Material Requisition To Resource Division |  |  | RTOR000178/2023-2024 | 75/CD | 11/01/2024 | 11/01/2024 | Resource Division | 14.85 | 0 | 0 | 0
6 | COOCHBEHAR | Dinhata-I | Coochbehar Division | BAISGURI KHANDA PIPED WATER SUPPLY SCHEME | SM/13284 | New | VEHICLE BILL |  |  | BILL/00476/2024-2025 | BP-218 | 31/07/2024 | 31/07/2024 | AJAD HOSSAIN | 0.03 | 0 | 0 | 0
7 | COOCHBEHAR | Dinhata-I | Coochbehar Division | BAISGURI KHANDA PIPED WATER SUPPLY SCHEME | SM/13284 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
8 | COOCHBEHAR | Dinhata-I | Coochbehar Division | BAISGURI KHANDA PIPED WATER SUPPLY SCHEME | SM/13284 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000280/2025-2026 | 787/CD | 23/05/2025 | 21/08/2025 | CONSTRUCTION DEVELOPMENT PROJECT | 79.37 | 0 | 0 | 0
9 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | BAISGURI KHANDA PIPED WATER SUPPLY SCHEME | SM/13284 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Baisguri Khanda water supply scheme, TW no I and II under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000883/2023-2024 | 2460/NMD-II | 11/08/2023 | 01/06/2025 | BLUE PINE | 21.48 | 0 | 0 | 100
Total | [13 empty] | 20569.25 | 0 | 0