## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | PETLAEPRA PIPED WATER SUPPLY SCHEME | SM/13285 | New | Material Requisition To Resource Division |  |  | RTOR000129/2023-2024 | 235/CD | 27/04/2023 | 27/04/2023 | Resource Division | 17.28 | 0 | 0 | 0
2 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | PETLAEPRA PIPED WATER SUPPLY SCHEME | SM/13285 | New | QUOTATION FOR NSC AT PETLA NEPRA P/H NO-II |  |  | BILL/01682/2023-2024 | BP-2023-24-305 | 08/09/2023 | 08/09/2023 | WBSEDCL | 4.25 | 0 | 0 | 0
3 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | PETLAEPRA PIPED WATER SUPPLY SCHEME | SM/13285 | New | QUOTATION FOR NSC AT PETLA NEPRA P/H NO-I |  |  | BILL/01681/2023-2024 | BP-2023-24-304 | 08/09/2023 | 08/09/2023 | WBSEDCL | 5.69 | 0 | 0 | 0
4 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | PETLAEPRA PIPED WATER SUPPLY SCHEME | SM/13285 | New | Execution of different works related to PETLAEPRA PWSS under JAL JEEVAN MISSION SE NBC1/PHED A. O.: 986/1-5/NBC-1; DT: 19-01-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000466/2022-2023 | 1517/CD | 19/01/2023 | 18/06/2023 | SHREE RANI SATI ENTERPRISE | 494.27 | 330.71 | 66.91 | 60
5 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | PETLAEPRA PIPED WATER SUPPLY SCHEME | SM/13285 | New | Material Requisition To Resource Division |  |  | RTOR000197/2023-2024 | 92/CD | 11/01/2024 | 11/01/2024 | Resource Division | 14.49 | 0 | 0 | 0
6 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | PETLAEPRA PIPED WATER SUPPLY SCHEME | SM/13285 | New | Execution of different works related to PETLAEPRA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000495/2023-2024 | 297/CD | 09/02/2024 | 04/04/2025 | SHREE RANI SATI ENTERPRISE | 80.89 | 32.83 | 40.58 | 30
7 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | PETLAEPRA PIPED WATER SUPPLY SCHEME | SM/13285 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
8 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | PETLAEPRA PIPED WATER SUPPLY SCHEME | SM/13285 | New | Laying DI P/Line & other allied works related to PETLAEPRA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000569/2023-2024 | 611/CD | 11/03/2024 | 06/03/2025 | SHREE RANI SATI ENTERPRISE | 31.76 | 22.65 | 71.32 | 65
9 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | PETLAEPRA PIPED WATER SUPPLY SCHEME | SM/13285 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000071/2025-2026 | 647/CD | 05/05/2025 | 03/08/2025 | Z STAR COMMOTRADE PVT LTD | 53.05 | 0 | 0 | 0
10 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | PETLAEPRA PIPED WATER SUPPLY SCHEME | SM/13285 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Petlaepra water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000796/2023-2024 | 2367/NMD-II | 08/08/2023 | 08/02/2025 | TAPAN BISWAS | 21.02 | 18.44 | 87.71 | 100
11 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | PETLAEPRA PIPED WATER SUPPLY SCHEME | SM/13285 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000277/2025-2026 | 737/CD | 17/05/2025 | 12/02/2026 | SANKAR CHAKRABORTY | 39.09 | 0 | 0 | 95
Total | [13 empty] | 20551.09 | 404.63 | 1.97