## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | PETLAEPRA PIPED WATER SUPPLY SCHEME | SM/13285 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Petlaepra water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000796/2023-2024 | 2367/NMD-II | 08/08/2023 | 07/09/2023 | TAPAN BISWAS | 21.02 | 0 | 0 | 0
2 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | PETLAEPRA PIPED WATER SUPPLY SCHEME | SM/13285 | New | QUOTATION FOR NSC AT PETLA NEPRA P/H NO-II |  |  | BILL/01682/2023-2024 | BP-2023-24-305 | 08/09/2023 |  | WBSEDCL | 4.25 | 0 | 0 | 0
3 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | PETLAEPRA PIPED WATER SUPPLY SCHEME | SM/13285 | New | QUOTATION FOR NSC AT PETLA NEPRA P/H NO-I |  |  | BILL/01681/2023-2024 | BP-2023-24-304 | 08/09/2023 |  | WBSEDCL | 5.69 | 0 | 0 | 0
4 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | PETLAEPRA PIPED WATER SUPPLY SCHEME | SM/13285 | New | Material Requisition To Resource Division |  |  | RTOR000197/2023-2024 | 92/CD | 11/01/2024 |  | Resource Division | 14.49 | 0 | 0 | 0
5 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | PETLAEPRA PIPED WATER SUPPLY SCHEME | SM/13285 | New | Execution of different works related to PETLAEPRA PWSS under JAL JEEVAN MISSION |  |  | ORD/000495/2023-2024 | 297/CD | 09/02/2024 | 09/04/2024 | SHREE RANI SATI ENTERPRISE | 80.89 | 0 | 0 | 0
6 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | PETLAEPRA PIPED WATER SUPPLY SCHEME | SM/13285 | New | Laying DI P/Line & other allied works related to PETLAEPRA PWSS under JAL JEEVAN MISSION |  |  | ORD/000569/2023-2024 | 611/CD | 11/03/2024 | 10/05/2024 | SHREE RANI SATI ENTERPRISE | 31.76 | 0 | 0 | 0
7 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | PETLAEPRA PIPED WATER SUPPLY SCHEME | SM/13285 | New | Execution of different works related to PETLAEPRA PWSS under JAL JEEVAN MISSION SE NBC1/PHED A. O.: 986/1-5/NBC-1; DT: 19-01-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000466/2022-2023 | 1517/CD | 19/01/2023 | 18/06/2023 | SHREE RANI SATI ENTERPRISE | 494.27 | 261.09 | 52.82 | 5
8 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | PETLAEPRA PIPED WATER SUPPLY SCHEME | SM/13285 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
Total | [13 empty] | 20441.67 | 261.09 | 1.28