## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | BARA MARICHA PIPED WATER SUPPLY SCHEME | SM/13286 | New | Material Requisition To Resource Division |  |  | RTOR000130/2023-2024 | 236/CD | 27/04/2023 | 27/04/2023 | Resource Division | 26.69 | 0 | 0 | 0
2 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | BARA MARICHA PIPED WATER SUPPLY SCHEME | SM/13286 | New | QUOTATION FOR NSC AT BARA MARICHA PH NO-I |  |  | BILL/01753/2023-2024 | BP-2023-24-355 | 03/10/2023 | 03/10/2023 | WBSEDCL | 5.59 | 0 | 0 | 0
3 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | BARA MARICHA PIPED WATER SUPPLY SCHEME | SM/13286 | New | QUOTATION FOR NSC AT BARA MARICHA PH NO-II |  |  | BILL/01754/2023-2024 | BP-2023-24-356 | 27/09/2023 | 27/09/2023 | WBSEDCL | 4.7 | 0 | 0 | 0
4 | COOCHBEHAR | Sitalkuchi | Northern Mechanical Division II | BARA MARICHA PIPED WATER SUPPLY SCHEME | SM/13286 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Bara Maricha Water Supply Scheme TW No.- I AND II under NMDII, PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001043/2023-2024 | 2692/NMD-II | 14/09/2023 | 14/10/2023 | M/S ANJALI ENTERPRISE | 20.05 | 0 | 0 | 60
5 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | BARA MARICHA PIPED WATER SUPPLY SCHEME | SM/13286 | New | EXECUTION OF DIFFERENT WORKS RELATED TO NIGAMNAGAR PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000620/2024-2025 | 2321/CD | 23/12/2024 | 21/02/2025 | TAPAN CHANDA | 96.52 | 0 | 0 | 0
6 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | BARA MARICHA PIPED WATER SUPPLY SCHEME | SM/13286 | New | EXECUTION OF DIFFERENT WORKS RELATED TO BARA MARICHA & BHOGDABARI PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000567/2024-2025 | 2252/CD | 23/12/2024 | 21/02/2025 | AMBITIOUS ENTERPRISE | 43.46 | 0 | 0 | 0
7 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | BARA MARICHA PIPED WATER SUPPLY SCHEME | SM/13286 | New | Material Requisition To Resource Division |  |  | RTOR000198/2023-2024 | 70/CD | 11/01/2024 | 11/01/2024 | Resource Division | 12.32 | 0 | 0 | 0
8 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | BARA MARICHA PIPED WATER SUPPLY SCHEME | SM/13286 | New | Execution of different works related to BARA MARICHA PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1293/1-5/NBC-1; Dt.: 17-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000606/2022-2023 | 1900/CD | 17/03/2023 | 21/01/2025 | UMEX POLYMERS PVT LTD | 367.91 | 0 | 0 | 25
9 | COOCHBEHAR | Sitalkuchi | Coochbehar Division | BARA MARICHA PIPED WATER SUPPLY SCHEME | SM/13286 | New | Execution of different works related to BARA MARICHA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000477/2023-2024 | 279/CD | 09/02/2024 | 15/08/2025 | GOUTAM KUMAR DAS | 93.42 | 0 | 0 | 80
Total | [13 empty] | 670.67 | 0 | 0