## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Haldibari | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme DEBOTTAR BAKSHIGANJ (BLOCK-HALDIBARI) | SM/13287 | New | QUOTATION FOR NEW SERVICE CONNECTION AT DEBOTTAR BOXIGANJ TW NO-I |  |  | BILL/00087/2023-2024 | BP-2023-24-75 | 15/05/2023 | 15/05/2023 | WBSEDCL | 0.93 | 0 | 0 | 0
2 | COOCHBEHAR | Haldibari | Coochbehar Division | Ground Water Based Piped Water Supply Scheme DEBOTTAR BAKSHIGANJ (BLOCK-HALDIBARI) | SM/13287 | New | FHTC AT SITALKUCHI PWSS Z-III |  |  | BILL/01044/2023-2024 | BP-500 | 22/09/2023 | 22/09/2023 | Z STAR COMMOTRADE PVT LTD | 28.95 | 0 | 0 | 0
3 | COOCHBEHAR | Haldibari | Coochbehar Division | Ground Water Based Piped Water Supply Scheme DEBOTTAR BAKSHIGANJ (BLOCK-HALDIBARI) | SM/13287 | New | EXECUTION OF MDIFFERENT WORKS AT DEBOTTAR BAKSHIGANJ PWSS |  |  | BILL/01107/2023-2024 | BP-546 | 07/10/2023 | 07/10/2023 | DAS ENTERPRISE | 35.11 | 0 | 0 | 0
4 | COOCHBEHAR | Haldibari | Coochbehar Division | Ground Water Based Piped Water Supply Scheme DEBOTTAR BAKSHIGANJ (BLOCK-HALDIBARI) | SM/13287 | New | Execution of different works related to DEBOTTAR BAKSHIGANJ PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION | ORD/000442/2022-2023 | 1419/CD | 29/12/2022 | 28/01/2023 | NARESH CH.MANDAL | 9.57 | 9.52 | 99.44 | 30
5 | COOCHBEHAR | Haldibari | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme DEBOTTAR BAKSHIGANJ (BLOCK-HALDIBARI) | SM/13287 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Debottar Bakshiganj Water Supply Scheme TW No.- I under NMD-II,PHE.Dte,Apd. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000667/2023-2024 | 2024/NMD-II | 26/07/2023 | 25/08/2023 | TAPAN BISWAS | 10.46 | 0 | 0 | 80
6 | COOCHBEHAR | Haldibari | Coochbehar Division | Ground Water Based Piped Water Supply Scheme DEBOTTAR BAKSHIGANJ (BLOCK-HALDIBARI) | SM/13287 | New | Execution of different works related to DEBOTTAR BAKSHIGANJ PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCHBEHAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000555/2022-2023 | 1702/CD | 13/02/2023 | 06/08/2025 | DAS ENTERPRISE | 120.12 | 45.14 | 37.58 | 70
7 | COOCHBEHAR | Haldibari | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme DEBOTTAR BAKSHIGANJ (BLOCK-HALDIBARI) | SM/13287 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector forGround Water Based Piped Water Supply Scheme DEBOTTAR BAKSHIGANJ (BLOCK-HALDIBARI) TW No.- II under Jal Jeevan Mission NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/000101/2025-2026 | 1252/NMD-II | 04/06/2025 | 04/07/2025 | SUBHRA ENTERPRISE | 11.32 | 0 | 0 | 0
8 | COOCHBEHAR | Haldibari | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme DEBOTTAR BAKSHIGANJ (BLOCK-HALDIBARI) | SM/13287 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of CoochBehar District in West Bengal. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/000063/2025-2026 | 1156/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 488.07 | 0 | 0 | 0
9 | COOCHBEHAR | Haldibari | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme DEBOTTAR BAKSHIGANJ (BLOCK-HALDIBARI) | SM/13287 | New | ELECTRIC QUOATION BILL FOR NSE AT DEBOTTAR BAXIGANJ PH-II |  |  | BILL/01714/2025-2026 |  | 21/08/2025 | 21/08/2025 | WBSEDCL | 5.01 | 0 | 0 | 0
Total | [13 empty] | 709.53 | 54.66 | 7.7