## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME BALASUNDAR BLOCK MATHABHANGA - II | SM/13288 | New | Execution of different works related to MATHABHANGA STACKYARD under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000452/2022-2023 | 3428/CD | 29/12/2022 | 28/01/2023 | ARUN KUMAR KARMAKAR | 4.3 | 0 | 0 | 100
2 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME BALASUNDAR BLOCK MATHABHANGA - II | SM/13288 | New | PAYMENT OF 06 NOS LABORATORY UNDER COB DIVISION, PHED |  |  | BILL/01085/2024-2025 | BP-221 | 01/08/2024 | 01/08/2024 | GREEN ECONOMY INISTIVES PVT LTD | 0.07 | 0 | 0 | 0
3 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME BALASUNDAR BLOCK MATHABHANGA - II | SM/13288 | New | Execution of different works related to BALASUNDAR PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 162/1-5/NBC-1; Dt.: 18-05-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000011/2023-2024 | 396/CD | 23/05/2023 | 11/06/2025 | AKANSHA COMMERCIAL PVT. LTD. | 396.38 | 0 | 0 | 38
4 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME BALASUNDAR BLOCK MATHABHANGA - II | SM/13288 | New | EXECUTION OF DIFFERENT WORKS (within BALASUNDAR and JORPATKI area) RELATED TO SHIKARPUR PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000678/2024-2025 | 83/CD | 17/01/2025 | 18/03/2025 | BIJOY ROY | 59.97 | 0 | 0 | 0
5 | COOCHBEHAR | Mathabhanga-II | Northern Mechanical Division II | GROUND WATER BASED PIPED WATER SUPPLY SCHEME BALASUNDAR BLOCK MATHABHANGA - II | SM/13288 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for BALASUNDAR water supply scheme, TW no -I,II and III under JJM under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/002038/2023-2024 | 1188/NMD-II | 11/03/2024 | 12/10/2025 | M/S SAJAHAN CHOWDHURY | 33.39 | 0 | 0 | 40
6 | COOCHBEHAR | Mathabhanga-II | Northern Mechanical Division II | GROUND WATER BASED PIPED WATER SUPPLY SCHEME BALASUNDAR BLOCK MATHABHANGA - II | SM/13288 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of CoochBehar District in West Bengal. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/000063/2025-2026 | 1156/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 488.07 | 0 | 0 | 0
7 | COOCHBEHAR | Mathabhanga-II | Northern Mechanical Division II | GROUND WATER BASED PIPED WATER SUPPLY SCHEME BALASUNDAR BLOCK MATHABHANGA - II | SM/13288 | New | Yard lighting arrangement at Head Work Site for Different PWSS (BALASUNDAR and others) under JJM in the BLOCK: Mathabhanga-II, DISTRICT: Coochbehar under NMD-II,PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/000168/2025-2026 | 1387/NMD-II | 26/06/2025 | 26/07/2025 | A.K SIKDAR | 18.14 | 0 | 0 | 0
8 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME BALASUNDAR BLOCK MATHABHANGA - II | SM/13288 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000077/2025-2026 | 650/CD | 05/05/2025 | 30/01/2026 | SUPER -TECH ENGINEERS'CO-OPERATIVE SOCIETY LIMITED | 69.03 | 0 | 0 | 60
9 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME BALASUNDAR BLOCK MATHABHANGA - II | SM/13288 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000074/2025-2026 | 789/CD | 23/05/2025 | 21/08/2025 | SHREE RANI SATI ENTERPRISE | 69.41 | 0 | 0 | 0
10 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | GROUND WATER BASED PIPED WATER SUPPLY SCHEME BALASUNDAR BLOCK MATHABHANGA - II | SM/13288 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000259/2025-2026 | 773/CD | 17/05/2025 | 15/08/2025 | RAJIB CHAKRABORTY | 35.99 | 0 | 0 | 0
Total | [13 empty] | 1174.75 | 0 | 0