## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Sitalkuchi Water Supply Scheme Zone-II to Accommodate FHTC in Sitalkuchi Block. | SM/13289 | Augmentation | Preparation of DPR for Augmentation of SITALKUCHI Piped Water Supply Scheme under Mathabhanga Sub-division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000291/2021-2022 | 1006/CD | 10/01/2022 | 30/01/2022 | RADIANT | 4.16 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Sitalkuchi Water Supply Scheme Zone-II to Accommodate FHTC in Sitalkuchi Block. | SM/13289 | Augmentation | Providing FHTC Laying of Pipe Line & other allied works at SITALKUCHI ZONE II PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000506/2022-2023 | 1232/CD | 28/11/2022 | 28/12/2022 | SOMNATH MUKHERJEE | 9.93 | 9.93 | 100 | 1
3 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground Water Based Sitalkuchi Water Supply Scheme Zone-II to Accommodate FHTC in Sitalkuchi Block. | SM/13289 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Sitalkhuchi water supply scheme, TW no I and II of Zone-I and TW I and II of Zone-II under Northern Mechanical Division-II, PHE Dte.APD |  |  | ORD/000811/2023-2024 | 2388/NMD-II | 09/08/2023 | 08/09/2023 | QUAZI NOZRUL ISLAM | 41.63 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Sitalkuchi Water Supply Scheme Zone-II to Accommodate FHTC in Sitalkuchi Block. | SM/13289 | Augmentation | Execution of different works related to SITALKUCHI Z2 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000779/2022-2023 | 1695/CD | 13/02/2023 | 05/03/2023 | GOUTAM KUMAR DAS | 6.69 | 0 | 0 | 100
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Sitalkuchi Water Supply Scheme Zone-II to Accommodate FHTC in Sitalkuchi Block. | SM/13289 | Augmentation | Execution of different works related to SITALKUCHI Z2 PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1345/1-5/NBC-1; Dt.: 24-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000560/2022-2023 | 1958/CD | 24/03/2023 | 21/08/2023 | Z STAR COMMOTRADE PVT LTD | 614.71 | 87.16 | 14.18 | 28
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Sitalkuchi Water Supply Scheme Zone-II to Accommodate FHTC in Sitalkuchi Block. | SM/13289 | Augmentation | Laying DI P/Line & other allied works related to STK Z II PWSS under JAL JEEVAN MISSION |  |  | ORD/000580/2023-2024 | 598/CD | 11/03/2024 | 10/05/2024 | Z STAR COMMOTRADE PVT LTD | 50.31 | 0 | 0 | 0
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Sitalkuchi Water Supply Scheme Zone-II to Accommodate FHTC in Sitalkuchi Block. | SM/13289 | Augmentation | EXECUTION OF DIFFERENT WOK AT SHUKARUR KUTHI PWSS |  |  | BILL/02047/2023-2024 | BP-1257-P2 | 28/03/2024 |  | GOUTAM KUMAR DAS | 5.79 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Sitalkuchi Water Supply Scheme Zone-II to Accommodate FHTC in Sitalkuchi Block. | SM/13289 | Augmentation | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 |  | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Sitalkuchi Water Supply Scheme Zone-II to Accommodate FHTC in Sitalkuchi Block. | SM/13289 | Augmentation | Execution of different works related to SITALKUCHI Z2 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000363/2023-2024 | 1394/CD | 05/12/2023 | 03/02/2024 | NO 1 GURIAHATI CO OP LABOUR CONTRACT AND CONSTRUCT SOCY LTD | 32.42 | 0 | 0 | 30
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground Water Based Sitalkuchi Water Supply Scheme Zone-II to Accommodate FHTC in Sitalkuchi Block. | SM/13289 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
Total | [13 empty] | 20610.63 | 97.1 | 0.47