## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | HASTABUD KASALDANGA PIPED WATER SUPPLY SCHEME. | SM/13290 | New | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 103/CD | 26/04/2023 | 26/04/2023 | Resource Division | 13.42 | 0 | 0 | 0
2 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | HASTABUD KASALDANGA PIPED WATER SUPPLY SCHEME. | SM/13290 | New | QUOTATION FOR NEW SERVICE CONNECTION AT HASTABUD KASHAL DANGA TW NO-II |  |  | BILL/00166/2023-2024 | BP-2023-24-121 | 18/05/2023 | 18/05/2023 | WBSEDCL | 1.06 | 0 | 0 | 0
3 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | HASTABUD KASALDANGA PIPED WATER SUPPLY SCHEME. | SM/13290 | New | QUOTATION FOR NEW SERVICE CONNECTION AT HASTABUD KASHAL DANGA TW NO-I |  |  | BILL/01813/2023-2024 | BP-2023-24-376 | 27/09/2023 | 27/09/2023 | WBSEDCL | 1.06 | 0 | 0 | 0
4 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | HASTABUD KASALDANGA PIPED WATER SUPPLY SCHEME. | SM/13290 | New | QUOTATION FOR NEW SERVICE CONNECTION AT HASTABUD KASHAL DANGA TW NO-I |  |  | BILL/00165/2023-2024 |  | 16/05/2023 | 16/05/2023 | WBSEDCL | 1.06 | 0 | 0 | 0
5 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | HASTABUD KASALDANGA PIPED WATER SUPPLY SCHEME. | SM/13290 | New | Execution of different works related to HASTABUD KASALDANGA PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1003/1-5/NBC-1; Dt.: 24-01-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000487/2022-2023 | 1552/CD | 24/01/2023 | 12/07/2025 | BABA LOKENATH UN EMPLOYED ENGINEERS CO OP SOCIETY LTD | 291.25 | 246.09 | 84.49 | 59
6 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | HASTABUD KASALDANGA PIPED WATER SUPPLY SCHEME. | SM/13290 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Hastabud Kasaldanga water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000740/2023-2024 | 2272/NMD-II | 31/07/2023 | 02/03/2025 | SANJIB SAHA | 19.77 | 9.23 | 46.68 | 80
7 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | HASTABUD KASALDANGA PIPED WATER SUPPLY SCHEME. | SM/13290 | New | Execution of different works related (Within area of CHAKCHAKA Z II) to HASTABUD KASALDANGA & CHAKCHAKA ZONE I PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000086/2024-2025 | 1190/CD | 24/06/2024 | 22/09/2024 | SWAPAN KR.SARKAR | 96.7 | 49.69 | 51.39 | 95
8 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | HASTABUD KASALDANGA PIPED WATER SUPPLY SCHEME. | SM/13290 | New | Execution of different works related to HASTABUD KASALDANGA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000028/2024-2025 | 1136/CD | 14/06/2024 | 09/02/2025 | RAJIB CHAKRABORTY | 23.36 | 0 | 0 | 50
9 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | HASTABUD KASALDANGA PIPED WATER SUPPLY SCHEME. | SM/13290 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000331/2025-2026 | 786/CD | 23/05/2025 | 20/09/2025 | M/S. MANDAL CONSTRUCTION | 9.56 | 0 | 0 | 30
Total | [13 empty] | 457.23 | 305.02 | 66.71