## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-I TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13316 | Augmentation | Providing FHTC Laying of Pipe Line & other allied works at SITALKUCHI ZONE I PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000507/2022-2023 | 1231/CD. | 28/11/2022 | 28/12/2022 | COOCH BEHAR U/E CO-OP-LAB. CONT. & CONSTN. SO-LTD | 9.93 | 9.93 | 100 | 1
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-I TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13316 | Augmentation | Execution of different works related to SITALKUCHI Z1 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000778/2022-2023 | 1694/CD | 13/02/2023 | 05/03/2023 | GOUTAM KUMAR DAS | 7.65 | 7.65 | 100 | 100
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-I TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13316 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000135/2023-2024 | 242/CD | 27/04/2023 | 27/04/2023 | Resource Division | 31.32 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-I TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13316 | Augmentation | Execution of different works related to SITALKUCHI Z1 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000362/2023-2024 | 1395/CD | 05/12/2023 | 03/02/2024 | NEW GOLDEN COOPARATIVE LAB CONT & CONSTN SOCY .LTD | 31.31 | 29.67 | 94.77 | 100
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-I TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13316 | Augmentation | Designing, Making & erecting of DB using logo tagline for Cooch Behar districts under Jal Jeevan Mission (JJM) Support Activities Part D | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000581/2023-2024 | 621/CD | 11/03/2024 | 10/05/2024 | LIMRA SOCIAL WELFARE SOCIETY | 25.98 | 25.83 | 99.41 | 100
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-I TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13316 | Augmentation | Execution of different works related to SITALKUCHI ZONE - I PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1213/1-5/NBC-1; Dt.: 01-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000582/2022-2023 | 1772/CD | 02/03/2023 | 18/08/2025 | Z STAR COMMOTRADE PVT LTD | 645.95 | 358.99 | 55.58 | 49
7 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-I TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13316 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Sitalkhuchi water supply scheme, TW no I and II of Zone-I and TW I and II of Zone-II under Northern Mechanical Division-II, PHE Dte.APD |  |  | ORD/000811/2023-2024 | 2388/NMD-II | 09/08/2023 | 08/09/2023 | QUAZI NOZRUL ISLAM | 41.63 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-I TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13316 | Augmentation | Hiring of Diesel Vehicle for inspection of site checking of FHTC and LDS, searching of land for different PWSS of Cooch Behar Sadar Sub-Division under Cooch Behar Division, PHE Dte. for 3 (Three) Months. (From May, 2023 to July, 2023). | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER | ORD/000231/2023-2024 | 124/CD/A | 26/04/2023 | 26/07/2023 | SANJAY KUMAR LAKHOTIA | 0.5 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-I TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13316 | Augmentation | Hiring of Diesel Vehicle for inspection of site checking of FHTC and LDS, searching of land for different PWSS of Cooch Behar Sadar Sub-Division under Cooch Behar Division, PHE Dte. for 2 (Two) Months. (From August, 2023 to September, 2023). | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER | ORD/000232/2023-2024 | 590/CD/A | 06/07/2023 | 06/09/2023 | SANJAY KUMAR LAKHOTIA | 0.34 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-I TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13316 | Augmentation | Hiring of Diesel Vehicle for Assistant Engineer, Cooch Behar RWS Sub-Division under Cooch Behar Division, PHED. for 03 (Three) Months. (From Nov. 2023 to January, 2024). | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER | ORD/000431/2023-2024 | 1242/CD | 31/10/2023 | 31/01/2024 | SANJAY KUMAR LAKHOTIA | 0.5 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-I TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13316 | Augmentation | Hiring of Diesel Vehicle for COB SADAR Assistant Engineer for inspection of site checking of FHTC and LDS, searching of land for different PWSS under Cooch Behar Division, PHE Dte. (From 01-07-24 to 30-06-2025). | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000468/2024-2025 | 1240/CD | 29/06/2024 | 29/06/2025 | ANIMESH DHAR CHOUDHURY | 1.92 | 0 | 0 | 0
12 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-I TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13316 | Augmentation | Laying DI P/Line & other allied works related to STK Z 1 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000590/2023-2024 | 627/CD | 11/03/2024 | 06/03/2025 | Z STAR COMMOTRADE PVT LTD | 95.68 | 0 | 0 | 55
13 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-I TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13316 | Augmentation | Laying DI P/Line & other allied works related to STK Z I PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000574/2023-2024 | 616/CD | 11/03/2024 | 10/05/2024 | Z STAR COMMOTRADE PVT LTD | 80.24 | 0 | 0 | 60
14 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-I TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13316 | Augmentation | Extension work for Hiring of Diesel Vehicle for Assistant Engineer, Cooch Behar Sadar Sub-Division under Cooch Behar Division, PHED for 03(three) Months. (From July 2024 to September, 2024)(WB-63/9203) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000365/2024-2025 | 1182/CD | 18/06/2024 | 18/09/2024 | PARAUDDIN MIA | 0.5 | 0.5 | 100 | 90
15 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-I TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13316 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000070/2025-2026 | 646/CD | 05/05/2025 | 03/08/2025 | Z STAR COMMOTRADE PVT LTD | 62.77 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-I TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13316 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000073/2025-2026 | 788/CD | 23/05/2025 | 21/08/2025 | SHREE RANI SATI ENTERPRISE | 75.53 | 0 | 0 | 0
Total | [13 empty] | 1111.75 | 432.57 | 38.91