## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata-I | Coochbehar Division | RUIER KHUTHI PIPED WATER SUPPLY SCHEME | SM/13317 | New | Execution of different works related to RUIER KHUTHI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1000/1-5/NBC-1; Dt.: 24-01-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000483/2022-2023 | 1548/CD | 24/01/2023 | 20/03/2025 | GEETA CONSTRUCTION | 462.18 | 406.96 | 88.05 | 98
2 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | RUIER KHUTHI PIPED WATER SUPPLY SCHEME | SM/13317 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for RUIERKUTHI water supply scheme, TW no I and II under Northern Mechanical Division-II, PHE Dte. Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000660/2023-2024 | 1974/NMD-II | 25/07/2023 | 24/08/2023 | M.S ENTERPRISE | 21.57 | 21.38 | 99.12 | 100
3 | COOCHBEHAR | Dinhata-I | Coochbehar Division | RUIER KHUTHI PIPED WATER SUPPLY SCHEME | SM/13317 | New | Material Requisition To Resource Division |  |  | RTOR000065/2023-2024 | 174/CD | 27/04/2023 | 27/04/2023 | Resource Division | 17.79 | 0 | 0 | 0
4 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | RUIER KHUTHI PIPED WATER SUPPLY SCHEME | SM/13317 | New | QUOTATION FOR NSC AT RUIERKUTHI PH NO-I |  |  | BILL/02191/2023-2024 | BP-2023-24-464 | 07/12/2023 | 07/12/2023 | WBSEDCL | 6.99 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata-I | Coochbehar Division | RUIER KHUTHI PIPED WATER SUPPLY SCHEME | SM/13317 | New | FHTC AT RASIKBILL Z-I |  |  | BILL/01038/2023-2024 | BP-478-P2 | 18/09/2023 | 18/09/2023 | HIRAK CONSTRUCTION | 7 | 0 | 0 | 0
6 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | RUIER KHUTHI PIPED WATER SUPPLY SCHEME | SM/13317 | New | QUOTATION FOR NSC AT RUIERKUTHI PH NO-II |  |  | BILL/02192/2023-2024 | BP-2023-24-463 | 07/12/2023 | 07/12/2023 | WBSEDCL | 4.22 | 0 | 0 | 0
7 | COOCHBEHAR | Dinhata-I | Coochbehar Division | RUIER KHUTHI PIPED WATER SUPPLY SCHEME | SM/13317 | New | Execution of different works related to RUIERKUTHI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000476/2023-2024 | 278/CD | 09/02/2024 | 09/04/2024 | GEETA CONSTRUCTION | 63.11 | 60.17 | 95.33 | 67
8 | COOCHBEHAR | Dinhata-I | Coochbehar Division | RUIER KHUTHI PIPED WATER SUPPLY SCHEME | SM/13317 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
9 | COOCHBEHAR | Dinhata-I | Coochbehar Division | RUIER KHUTHI PIPED WATER SUPPLY SCHEME | SM/13317 | New | Extension work for Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-D) under RUIER KHUTHI PIPED WATER SUPPLY SCHEME | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000344/2024-2025 | 860/CD | 12/04/2024 | 12/08/2024 | SENGUPTA ENTERPRISE | 0.97 | 0.97 | 100 | 100
10 | COOCHBEHAR | Dinhata-I | Coochbehar Division | RUIER KHUTHI PIPED WATER SUPPLY SCHEME | SM/13317 | New | Extension work for Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-E) under RUIER KHUTHI PIPED WATER SUPPLY SCHEME | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000345/2024-2025 | 862/CD | 12/04/2024 | 12/08/2024 | SENGUPTA ENTERPRISE | 0.97 | 0.97 | 100 | 100
11 | COOCHBEHAR | Dinhata-I | Coochbehar Division | RUIER KHUTHI PIPED WATER SUPPLY SCHEME | SM/13317 | New | Extension work for Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-F) under RUIER KHUTHI PIPED WATER SUPPLY SCHEME | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000346/2024-2025 | 978/CD | 23/04/2024 | 23/08/2024 | SENGUPTA ENTERPRISE | 0.97 | 0.97 | 100 | 100
12 | COOCHBEHAR | Dinhata-I | Coochbehar Division | RUIER KHUTHI PIPED WATER SUPPLY SCHEME | SM/13317 | New | EXECUTION OF DIFFERENT WORK AT SHALBARI ZONE-IIN PWSS |  |  | BILL/02040/2023-2024 | BP-999 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 47.55 | 0 | 0 | 0
13 | COOCHBEHAR | Dinhata-I | Coochbehar Division | RUIER KHUTHI PIPED WATER SUPPLY SCHEME | SM/13317 | New | EXECUTION OF DIFFERENT WORKS (within NAJIRGANJ, BHANGRI PRATHAM KHANDA, RUIER KHUTHI & HARIBHANGA KHATTIMARI area) RELATED TO Bhulki PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000655/2024-2025 | 84/CD | 17/01/2025 | 13/11/2025 | BIJOY ROY | 84.6 | 0 | 0 | 40
14 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | RUIER KHUTHI PIPED WATER SUPPLY SCHEME | SM/13317 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of CoochBehar District in West Bengal. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/000063/2025-2026 | 1156/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 488.07 | 0 | 0 | 0
15 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | RUIER KHUTHI PIPED WATER SUPPLY SCHEME | SM/13317 | New | Solarization of grid connected pumping installation at Different PWSS at Coochbehar-II Block in the dist.of Coochbehar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000136/2025-2026 | 1336/NMD-II | 18/06/2025 | 16/09/2025 | M R S ELECTRICAL | 21.84 | 0 | 0 | 0
16 | COOCHBEHAR | Dinhata-I | Coochbehar Division | RUIER KHUTHI PIPED WATER SUPPLY SCHEME | SM/13317 | New | Material Requisition To Resource Division |  |  | RTOR000028/2024-2025 | 71/CD | 15/01/2025 | 15/01/2025 | Resource Division | 30.8 | 0 | 0 | 0
Total | [13 empty] | 21047.92 | 491.42 | 2.33