## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata - I | Coochbehar Division | RUIER KHUTHI PIPED WATER SUPPLY SCHEME | SM/13317 | New | Material Requisition To Resource Division |  |  | RTOR000065/2023-2024 | 174/CD | 27/04/2023 |  | Resource Division | 17.79 | 0 | 0 | 0
2 | COOCHBEHAR | Dinhata - I | Coochbehar Division | RUIER KHUTHI PIPED WATER SUPPLY SCHEME | SM/13317 | New | FHTC AT RASIKBILL Z-I |  |  | BILL/01038/2023-2024 | BP-478-P2 | 18/09/2023 |  | HIRAK CONSTRUCTION | 7 | 0 | 0 | 0
3 | COOCHBEHAR | Dinhata - I | Northern Mechanical Division II | RUIER KHUTHI PIPED WATER SUPPLY SCHEME | SM/13317 | New | QUOTATION FOR NSC AT RUIERKUTHI PH NO-I |  |  | BILL/02191/2023-2024 | BP-2023-24-464 | 07/12/2023 |  | WBSEDCL | 6.99 | 0 | 0 | 0
4 | COOCHBEHAR | Dinhata - I | Northern Mechanical Division II | RUIER KHUTHI PIPED WATER SUPPLY SCHEME | SM/13317 | New | QUOTATION FOR NSC AT RUIERKUTHI PH NO-II |  |  | BILL/02192/2023-2024 | BP-2023-24-463 | 07/12/2023 |  | WBSEDCL | 4.22 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata - I | Coochbehar Division | RUIER KHUTHI PIPED WATER SUPPLY SCHEME | SM/13317 | New | EXECUTION OF DIFFERENT WORK AT SHALBARI ZONE-IIN PWSS |  |  | BILL/02040/2023-2024 | BP-999 | 03/02/2024 |  | M/S B PAUL AND COMPANY | 47.55 | 0 | 0 | 0
6 | COOCHBEHAR | Dinhata - I | Northern Mechanical Division II | RUIER KHUTHI PIPED WATER SUPPLY SCHEME | SM/13317 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for RUIERKUTHI water supply scheme, TW no I and II under Northern Mechanical Division-II, PHE Dte. Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000660/2023-2024 | 1974/NMD-II | 25/07/2023 | 24/08/2023 | M.S ENTERPRISE | 21.57 | 10.15 | 47.04 | 100
7 | COOCHBEHAR | Dinhata - I | Coochbehar Division | RUIER KHUTHI PIPED WATER SUPPLY SCHEME | SM/13317 | New | Execution of different works related to RUIERKUTHI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000476/2023-2024 | 278/CD | 09/02/2024 | 09/04/2024 | GEETA CONSTRUCTION | 63.11 | 21.21 | 33.6 | 67
8 | COOCHBEHAR | Dinhata - I | Coochbehar Division | RUIER KHUTHI PIPED WATER SUPPLY SCHEME | SM/13317 | New | Execution of different works related to RUIER KHUTHI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1000/1-5/NBC-1; Dt.: 24-01-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000483/2022-2023 | 1548/CD | 24/01/2023 | 23/06/2023 | GEETA CONSTRUCTION | 462.18 | 365.35 | 79.05 | 18
9 | COOCHBEHAR | Dinhata - I | Coochbehar Division | RUIER KHUTHI PIPED WATER SUPPLY SCHEME | SM/13317 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
10 | COOCHBEHAR | Dinhata - I | Coochbehar Division | RUIER KHUTHI PIPED WATER SUPPLY SCHEME | SM/13317 | New | Extension work for Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-D) under RUIER KHUTHI PIPED WATER SUPPLY SCHEME | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000344/2024-2025 | 860/CD | 12/04/2024 | 10/08/2024 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 100
11 | COOCHBEHAR | Dinhata - I | Coochbehar Division | RUIER KHUTHI PIPED WATER SUPPLY SCHEME | SM/13317 | New | Extension work for Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-E) under RUIER KHUTHI PIPED WATER SUPPLY SCHEME | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000345/2024-2025 | 862/CD | 12/04/2024 | 10/08/2024 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 100
12 | COOCHBEHAR | Dinhata - I | Coochbehar Division | RUIER KHUTHI PIPED WATER SUPPLY SCHEME | SM/13317 | New | Extension work for Uploading charges of (https://ejalshakti.gov.in/imisreports/IMISReportLogin.aspx) related to FHTC under Jal Jeevan Mission in presence of JJM Login authority under Cooch Behar Division, PHE Dte. (Part-F) under RUIER KHUTHI PIPED WATER SUPPLY SCHEME | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000346/2024-2025 | 978/CD | 23/04/2024 | 21/08/2024 | SENGUPTA ENTERPRISE | 0.97 | 0 | 0 | 100
Total | [13 empty] | 20422.61 | 396.71 | 1.94