## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata - II | Northern Mechanical Division II | KOCHABARI PIPED WATER SUPPLY SCHEME. | SM/13342 | New | QUOTATION FOR NEW SERVICE CONNECTION AT khochabari TW II |  |  | BILL/00013/2023-2024 | BP-2023-24-30 | 28/04/2023 |  | WBSEDCL | 1.05 | 0 | 0 | 0
2 | COOCHBEHAR | Dinhata - II | Northern Mechanical Division II | KOCHABARI PIPED WATER SUPPLY SCHEME. | SM/13342 | New | QUOTATION FOR NEW SERVICE CONNECTION AT KHOCHABARI W/SS TW I |  |  | BILL/00021/2023-2024 | BP-2023-24-32 | 28/04/2023 |  | WBSEDCL | 1.05 | 0 | 0 | 0
3 | COOCHBEHAR | Dinhata - II | Coochbehar Division | KOCHABARI PIPED WATER SUPPLY SCHEME. | SM/13342 | New | Exc. of difft. work at kauardara |  |  | BILL/00586/2023-2024 | BP-157-P | 24/05/2023 |  | SAIMONS CO- OPARATIVE LAB CONT & CONSTN SOCY LTD | 16.07 | 0 | 0 | 0
4 | COOCHBEHAR | Dinhata - II | Northern Mechanical Division II | KOCHABARI PIPED WATER SUPPLY SCHEME. | SM/13342 | New | QUOTATION DIVERSION WORKS OF AE,CMSD KOHACHABARI PWSS P/H NO-I |  |  | BILL/02453/2023-2024 | null | 16/01/2024 |  | WBSEDCL | 14.08 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata - II | Northern Mechanical Division II | KOCHABARI PIPED WATER SUPPLY SCHEME. | SM/13342 | New | Additional quotation for new service connection at Kochabari PWSS, P/H-I. |  |  | BILL/02420/2023-2024 | BP-2023-24-548 | 17/01/2024 |  | WBSEDCL | 14.08 | 0 | 0 | 0
6 | COOCHBEHAR | Dinhata - II | Northern Mechanical Division II | KOCHABARI PIPED WATER SUPPLY SCHEME. | SM/13342 | New | Additional quotation for new service connection at Kochabari PWSS, P/H-I. |  |  | BILL/02420/2023-2024 | BP-2023-24-548 | 17/01/2024 |  | WBSEDCL | 14.08 | 0 | 0 | 0
7 | COOCHBEHAR | Dinhata - II | Coochbehar Division | KOCHABARI PIPED WATER SUPPLY SCHEME. | SM/13342 | New | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 |  | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
8 | COOCHBEHAR | Dinhata - II | Coochbehar Division | KOCHABARI PIPED WATER SUPPLY SCHEME. | SM/13342 | New | Execution of different works related to KOCHABARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000167/2023-2024 | 944/CD | 04/09/2023 | 03/12/2023 | HARIDAS GHOSH | 97.39 | 0 | 0 | 85
9 | COOCHBEHAR | Dinhata - II | Coochbehar Division | KOCHABARI PIPED WATER SUPPLY SCHEME. | SM/13342 | New | Execution of different works related to KOCHABARI PWSS under JAL JEEVAN MISSION SE NBC1/PHED A. O.: 983/1-5/NBC-1; DT: 19-01-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000463/2022-2023 | 1514/CD | 19/01/2023 | 18/06/2023 | HARIDAS GHOSH | 402.06 | 262.76 | 65.35 | 88
10 | COOCHBEHAR | Dinhata - II | Northern Mechanical Division II | KOCHABARI PIPED WATER SUPPLY SCHEME. | SM/13342 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for KOCHABARI water supply scheme, TW no I and II under JJM under NMD-II, PHE Dte. APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000692/2023-2024 | 2192/NMD-II | 28/07/2023 | 27/08/2023 | DILIP MAHATO | 21.07 | 19.81 | 94.06 | 80
Total | [13 empty] | 636.62 | 282.57 | 44.39