## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentatin of Bajejama Chilakhana Zone-III PWSS Accomodate FHTC in TFG-I BLOCK | SM/13378 | Augmentation | Execution of different works related to AUG. of BAJEJAMA CHILAKHANA ZONE-III PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1006/1-5/NBC-1; Dt.: 24-01-23 | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000500/2022-2023 | 1565/CD | 24/01/2023 | 23/06/2023 | HARIDAS GHOSH | 345.87 | 194.14 | 56.13 | 50
2 | COOCHBEHAR |  | Coochbehar Division | Augmentatin of Bajejama Chilakhana Zone-III PWSS Accomodate FHTC in TFG-I BLOCK | SM/13378 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
3 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentatin of Bajejama Chilakhana Zone-III PWSS Accomodate FHTC in TFG-I BLOCK | SM/13378 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Bajejama Chilakhana (Tufangunj-I Block) water supply scheme, TW no I and II of Zone-III under Northern Mechanical Division-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000807/2023-2024 | 2368/NMD-II | 08/08/2023 | 07/09/2023 | SOUMEN ELECTRIC | 22.33 | 0 | 0 | 40
Total | [13 empty] | 20157.49 | 194.14 | 0.96