## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-III TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13379 | Augmentation | Providing FHTC Laying of Pipe Line & other allied works at SITALKUCHI ZONE III PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000505/2022-2023 | 1233/CD | 28/11/2022 | 28/12/2022 | RAJAT ROY | 9.93 | 2.03 | 20.47 | 1
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-III TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13379 | Augmentation | Preparation of DPR for Augmentation of SITALKUCHI (Zone-III) Piped Water Supply Scheme under MATHABHANGA Sub-Division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000161/2022-2023 | 620/CD | 16/08/2022 | 05/09/2022 | RADIANT | 3.41 | 0 | 0 | 1
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-III TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13379 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000134/2023-2024 | 243/CD | 27/04/2023 | 27/04/2023 | Resource Division | 48.39 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-III TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13379 | Augmentation | FHTC AT SITALKUCHI PWSS |  |  | BILL/01083/2023-2024 | BP-551 | 11/10/2023 | 11/10/2023 | GOUTAM KUMAR DAS | 6.69 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-III TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13379 | Augmentation | FHTC AT B/ GODAIKHORA PWSS |  |  | BILL/00630/2022-2023 | BP-778-22-23-P1 | 14/03/2023 | 14/03/2023 | BIJOY ROY | 0 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-III TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13379 | Augmentation | FHTC AT PWSS |  |  | BILL/00678/2022-2023 | BP-737-22-23-P1 | 06/03/2023 | 06/03/2023 | M/S S.DAS AND ENTERPRISE | 5.4 | 0 | 0 | 0
7 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-III TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13379 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT PUTIA SITALKUCHI (AUG) Z-III,PH NO-II |  |  | BILL/00151/2023-2024 | BP-2023-24-108 | 18/05/2023 | 18/05/2023 | WBSEDCL | 0.98 | 0 | 0 | 0
8 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-III TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13379 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT PUTIA SITALKUCHI (AUG) Z-III,PH NO-I |  |  | BILL/00150/2023-2024 | BP-2023-24-109 | 18/05/2023 | 18/05/2023 | WBSEDCL | 0.98 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-III TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13379 | Augmentation | EXECUTION OF DIFFERENT WORK AT ICHHAMARI PWSS |  |  | BILL/02062/2023-2024 | BP-1128-P2 | 02/03/2024 | 02/03/2024 | ASHIM KUMAR CHAKRABORTY | 23.53 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-III TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13379 | Augmentation | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-III TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13379 | Augmentation | Execution of different works related to SITALKUCHI ZONE -III PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1014/1-5/NBC-1; Dt.: 24-01-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000492/2022-2023 | 1557/CD | 24/01/2023 | 09/12/2025 | Z STAR COMMOTRADE PVT LTD | 492.69 | 313.72 | 63.67 | 92
12 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-III TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13379 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augumentation of Sitalkuchi Zone-III Water Supply Scheme TW No.- I II and III under NMD-II,PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000725/2023-2024 | 2290/NMD-II | 31/07/2023 | 30/08/2023 | CHOWDHURY AND BASU ENTERPRISE | 31.23 | 18.54 | 59.39 | 60
13 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-III TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13379 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
14 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-III TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13379 | Augmentation | Laying DI P/Line & other allied works related to STK Z III PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000585/2023-2024 | 597/CD | 11/03/2024 | 06/03/2025 | Z STAR COMMOTRADE PVT LTD | 26.99 | 0 | 0 | 60
15 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-III TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13379 | Augmentation | Laying DI P/Line & other allied works related to STK Z III PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000599/2023-2024 | 644/CD | 11/03/2024 | 06/03/2025 | Z STAR COMMOTRADE PVT LTD | 73.87 | 0 | 0 | 65
16 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-III TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13379 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000071/2025-2026 | 647/CD | 05/05/2025 | 03/08/2025 | Z STAR COMMOTRADE PVT LTD | 53.05 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-III TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13379 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000072/2025-2026 | 648/CD | 05/05/2025 | 03/08/2025 | Z STAR COMMOTRADE PVT LTD | 47.83 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-III TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13379 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000280/2025-2026 | 787/CD | 23/05/2025 | 21/08/2025 | CONSTRUCTION DEVELOPMENT PROJECT | 79.37 | 0 | 0 | 0
19 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-III TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13379 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO SITALKUCHI - 1 PWSS UNDER JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000685/2024-2025 | 221/CD | 12/02/2025 | 13/04/2025 | ARUN KUMAR KARMAKAR | 6.86 | 0 | 0 | 50
Total | [13 empty] | 20756.2 | 334.29 | 1.61