## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Sitalkuchi water supply scheme Zone- V to accommodate FHTC in Sitalkuchi Block | SM/13380 | Augmentation | Providing FHTC Laying of Pipe Line & other allied works at SITALKUCHI ZONE V PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000503/2022-2023 | 1235/CD | 28/11/2022 | 28/12/2022 | RAJU GHOSH | 9.93 | 9.93 | 100 | 1
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Sitalkuchi water supply scheme Zone- V to accommodate FHTC in Sitalkuchi Block | SM/13380 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000132/2023-2024 | 238/CD | 27/04/2023 | 27/04/2023 | Resource Division | 42.24 | 0 | 0 | 0
3 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground water based Sitalkuchi water supply scheme Zone- V to accommodate FHTC in Sitalkuchi Block | SM/13380 | Augmentation | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT SITALKUCHI ZONE-V TW NO. I |  |  | BILL/00275/2024-2025 | BP-74/24-25 | 15/05/2024 | 15/05/2024 | WBSEDCL | 6.09 | 0 | 0 | 0
4 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground water based Sitalkuchi water supply scheme Zone- V to accommodate FHTC in Sitalkuchi Block | SM/13380 | Augmentation | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT SITALKUCHI ZONE-V TW NO II. |  |  | BILL/00278/2024-2025 | BP-75/24-25 | 16/05/2024 | 16/05/2024 | WBSEDCL | 5.52 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Sitalkuchi water supply scheme Zone- V to accommodate FHTC in Sitalkuchi Block | SM/13380 | Augmentation | Execution of different works related to SITALKUCHI Z5 PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1214/1-5/NBC-1; Dt.: 01-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000532/2022-2023 | 1776/CD | 02/03/2023 | 21/03/2025 | Z STAR COMMOTRADE PVT LTD | 538.58 | 270.08 | 50.15 | 80
6 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground water based Sitalkuchi water supply scheme Zone- V to accommodate FHTC in Sitalkuchi Block | SM/13380 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Sitalkhuchi water supply scheme, TW no I,II , III and IV of Zone-V under Northern Mechanical Division-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000804/2023-2024 | 2369/NMD-II | 08/08/2023 | 06/09/2025 | M/S P.P ELECTRICALS | 41.62 | 0 | 0 | 40
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Sitalkuchi water supply scheme Zone- V to accommodate FHTC in Sitalkuchi Block | SM/13380 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 111.75 | 0.56 | 20
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Sitalkuchi water supply scheme Zone- V to accommodate FHTC in Sitalkuchi Block | SM/13380 | Augmentation | Laying DI P/Line & other allied works related to STK Z V PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000570/2023-2024 | 612/CD | 11/03/2024 | 06/03/2025 | Z STAR COMMOTRADE PVT LTD | 43.86 | 0 | 0 | 60
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Sitalkuchi water supply scheme Zone- V to accommodate FHTC in Sitalkuchi Block | SM/13380 | Augmentation | Laying DI P/Line & other allied works related to STK Z V PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000594/2023-2024 | 634/CD | 11/03/2024 | 06/03/2025 | Z STAR COMMOTRADE PVT LTD | 98.29 | 0 | 0 | 30
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Sitalkuchi water supply scheme Zone- V to accommodate FHTC in Sitalkuchi Block | SM/13380 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Tufanganj-II, Augmentation of Sitalkuchi Zone-V Piped Water Supply Scheme under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000640/2024-2025 | 1855/CD | 28/10/2024 | 28/01/2025 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Sitalkuchi water supply scheme Zone- V to accommodate FHTC in Sitalkuchi Block | SM/13380 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Cooch Behar-I, Augmentation of Sitalkuchi Zone-V Piped Water Supply Scheme under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | Junior Engineer, Head Quarter | ORD/000637/2024-2025 | 1852/CD | 28/10/2024 | 28/01/2025 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
12 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Sitalkuchi water supply scheme Zone- V to accommodate FHTC in Sitalkuchi Block | SM/13380 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Cooch Behar-II, Augmentation of Sitalkuchi Zone-V Piped Water Supply Scheme under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | Junior Engineer, Head Quarter | ORD/000638/2024-2025 | 1853/CD | 28/10/2024 | 28/01/2025 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
13 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Sitalkuchi water supply scheme Zone- V to accommodate FHTC in Sitalkuchi Block | SM/13380 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Tufanganj-I, Augmentation of Sitalkuchi Zone-V Piped Water Supply Scheme under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000639/2024-2025 | 1854/CD | 28/10/2024 | 28/01/2025 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
14 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Sitalkuchi water supply scheme Zone- V to accommodate FHTC in Sitalkuchi Block | SM/13380 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000263/2025-2026 | 771/CD | 17/05/2025 | 11/02/2026 | UNIQUE ENGINEERS CO OP SOCIETY LTD | 29.2 | 0 | 0 | 75
Total | [13 empty] | 20608.56 | 395.7 | 1.92