## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Shikarpur PWSS to accommodate FHTC in Tufanganj-I Block | SM/13381 | Augmentation | Execution of different works related to SHIKARPUR P1 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000438/2022-2023 | 1415/CD | 29/12/2022 | 28/01/2023 | BIJAN KR.ROY | 9.57 | 4.08 | 42.59 | 100
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Shikarpur PWSS to accommodate FHTC in Tufanganj-I Block | SM/13381 | Augmentation | Preparation of DPR for Augmentation of Sikarpar Piped Water Supply Scheme under Tufanganj Sub-division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000294/2021-2022 | 1009/CD | 10/01/2022 | 30/01/2022 | RADIANT | 2.96 | 2.96 | 100 | 1
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Shikarpur PWSS to accommodate FHTC in Tufanganj-I Block | SM/13381 | Augmentation | Execution of different works related to SHIKARPUR P2 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000439/2022-2023 | 1416/CD | 29/12/2022 | 28/01/2023 | MA MAHAMAYA UNP.CO-OP LABOUR CONTRACT AND CONST SOCIETY LTD. | 9.57 | 9.57 | 100 | 100
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Shikarpur PWSS to accommodate FHTC in Tufanganj-I Block | SM/13381 | Augmentation | Providing FHTC with replacing old damaged pipe line with new UPVC pipe line other allied works at SHIKARPUR PWSS under Tufanganj Sub-Division, PHED. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000896/2022-2023 | 204/TFG | 05/07/2022 | 17/09/2025 | PARITOSH DATTA | 4.1 | 1.56 | 38.02 | 100
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Shikarpur PWSS to accommodate FHTC in Tufanganj-I Block | SM/13381 | Augmentation | FHTC AT SHIKARAPUR PWSS |  |  | VCH/001037/2022-2023 | 428 | 30/11/2022 | 30/11/2022 | PARITOSH DUTTA | 8.03 | 0 | 0 | 0
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Shikarpur PWSS to accommodate FHTC in Tufanganj-I Block | SM/13381 | Augmentation | Execution of different works related to AUG. SIKARPUR PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1287/1-5/NBC-1; Dt.: 17-03-23 | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000619/2022-2023 | 1905/CD | 17/03/2023 | 26/11/2026 | ASHIM KUMAR CHAKRABORTY | 497.65 | 230.49 | 46.32 | 40
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Shikarpur PWSS to accommodate FHTC in Tufanganj-I Block | SM/13381 | Augmentation | Name of Work: Execution of different works related to AUG of SHIKARPUR (TFG) PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000273/2023-2024 | 1041/CD | 22/09/2023 | 21/11/2023 | ASHIM KUMAR CHAKRABORTY | 68.38 | 0 | 0 | 70
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Shikarpur PWSS to accommodate FHTC in Tufanganj-I Block | SM/13381 | Augmentation | Execution of different works related to TUFANGANJ M AREA at SHIKARPUR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000328/2023-2024 | 1311/CD | 24/11/2023 | 23/01/2024 | JANE MIA | 9.06 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Shikarpur PWSS to accommodate FHTC in Tufanganj-I Block | SM/13381 | Augmentation | Execution of different works related to TFG HOSPITAL under SHIKARPUR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000331/2023-2024 | 1317/CD | 24/11/2023 | 23/01/2024 | JANE MIA | 9.06 | 0 | 0 | 0
10 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground water based Shikarpur PWSS to accommodate FHTC in Tufanganj-I Block | SM/13381 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augumentation of Shikarpur (Tufangunj-I Block) water supply scheme, TW no III and IV under Northern Mechanical Division-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000706/2023-2024 | 2222/NMD-II | 28/07/2023 | 27/08/2023 | SUMON ELECTRICAL | 21.08 | 20.78 | 98.58 | 100
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Shikarpur PWSS to accommodate FHTC in Tufanganj-I Block | SM/13381 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000044/2023-2024 | 149/CD | 27/04/2023 | 27/04/2023 | Resource Division | 27.72 | 0 | 0 | 0
12 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground water based Shikarpur PWSS to accommodate FHTC in Tufanganj-I Block | SM/13381 | Augmentation | QUOTATION FOR NSC AT SHIKARPUR TFG PH NO II |  |  | BILL/01060/2023-2024 | BP-2023-24-256 | 02/08/2023 | 02/08/2023 | WBSEDCL | 8.68 | 0 | 0 | 0
13 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Ground water based Shikarpur PWSS to accommodate FHTC in Tufanganj-I Block | SM/13381 | Augmentation | QUOTATION FOR NSC AT SIKARPUR TFG PH NO -III |  |  | BILL/01818/2023-2024 | BP-2023-24-327 | 27/09/2023 | 27/09/2023 | WBSEDCL | 6.46 | 0 | 0 | 0
14 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Shikarpur PWSS to accommodate FHTC in Tufanganj-I Block | SM/13381 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO Santoshpur zone-II & SHIKARPUR PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000584/2024-2025 | 2267/CD | 23/12/2024 | 21/02/2025 | SANJAY MANDAL | 83.25 | 9.4 | 11.3 | 30
15 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Shikarpur PWSS to accommodate FHTC in Tufanganj-I Block | SM/13381 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2024-2025 | 1540/CD | 16/08/2024 | 16/08/2024 | Resource Division | 15.1 | 0 | 0 | 0
16 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Shikarpur PWSS to accommodate FHTC in Tufanganj-I Block | SM/13381 | Augmentation | EXECUTION OF DIFFERENT WORKS (within BALASUNDAR and JORPATKI area) RELATED TO SHIKARPUR PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000678/2024-2025 | 83/CD | 17/01/2025 | 18/03/2025 | BIJOY ROY | 59.97 | 0 | 0 | 0
17 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Ground water based Shikarpur PWSS to accommodate FHTC in Tufanganj-I Block | SM/13381 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000273/2025-2026 | 742/CD | 17/05/2025 | 13/11/2025 | AASHIRBAD ENTERPRISE | 83.45 | 0 | 0 | 70
Total | [13 empty] | 924.09 | 278.84 | 30.17