## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Santoshpur zone-II PWSS Accommodate FHTC in TFG-I Block . | SM/13382 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000035/2022-2023 | 1348/CD | 19/12/2022 | 19/12/2022 | Resource Division | 61.6 | 0 | 0 | 0
2 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Santoshpur zone-II PWSS Accommodate FHTC in TFG-I Block . | SM/13382 | Augmentation | QUOTATION FOR NSC AT SANTOSHPUR Z-II |  |  | BILL/01056/2023-2024 | BP-2023-24-253 | 02/08/2023 | 02/08/2023 | WBSEDCL | 6.42 | 0 | 0 | 0
3 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Santoshpur zone-II PWSS Accommodate FHTC in TFG-I Block . | SM/13382 | Augmentation | QUOTATION FOR NSC AT SANTOSHPUR Z-II,PH NO II |  |  | BILL/01057/2023-2024 | BP-2023-24-254 | 02/08/2023 | 02/08/2023 | WBSEDCL | 6.99 | 0 | 0 | 0
4 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Santoshpur zone-II PWSS Accommodate FHTC in TFG-I Block . | SM/13382 | Augmentation | New service connection at Santoshpur PWSS, P/H-II |  |  | BILL/02753/2023-2024 | BP-2023-24-626 | 21/02/2024 | 21/02/2024 | WBSEDCL | 1.34 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Santoshpur zone-II PWSS Accommodate FHTC in TFG-I Block . | SM/13382 | Augmentation | Execution of different works related to AUG. of SANTOSHPUR ZONE II PWSS under JAL JEEVAN MISSION. SE,NBC-1,PHED A.O. No.: 32/1-5/NBC-1; Dt.: 13-04-23 | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000039/2023-2024 | 46/CD | 17/04/2023 | 14/09/2023 | ASHIM KUMAR CHAKRABORTY | 268.06 | 229.21 | 85.51 | 20
6 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Santoshpur zone-II PWSS Accommodate FHTC in TFG-I Block . | SM/13382 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augmentation of Santoshpur water supply scheme, TW no III of Zone-I and TW No-III of Zone-II under Northern Mechanical Division-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000821/2023-2024 | 2399/NMD-II | 09/08/2023 | 08/09/2023 | P K ENGINEERING | 20.78 | 0 | 0 | 100
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Santoshpur zone-II PWSS Accommodate FHTC in TFG-I Block . | SM/13382 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO Santoshpur zone-II & SHIKARPUR PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000584/2024-2025 | 2267/CD | 23/12/2024 | 21/02/2025 | SANJAY MANDAL | 83.25 | 0 | 0 | 30
8 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Santoshpur zone-II PWSS Accommodate FHTC in TFG-I Block . | SM/13382 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Santoshpur Water Supply Scheme TW No.- II of Zone- II under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/001225/2024-2025 | 845/NMD-II | 11/03/2025 | 10/04/2025 | D.K AND SONS | 10.41 | 0 | 0 | 80
9 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Santoshpur zone-II PWSS Accommodate FHTC in TFG-I Block . | SM/13382 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT Santoshpur zone-II PWSS UNDER Cooch Behar Division PHED | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000686/2024-2025 | 222/CD | 12/02/2025 | 13/04/2025 | GOUTAM KUMAR DAS | 22.83 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Santoshpur zone-II PWSS Accommodate FHTC in TFG-I Block . | SM/13382 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000095/2025-2026 | 736/CD | 17/05/2025 | 13/11/2025 | AASHIRBAD ENTERPRISE | 42.14 | 0 | 0 | 85
11 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Santoshpur zone-II PWSS Accommodate FHTC in TFG-I Block . | SM/13382 | Augmentation | EXECUTION OF DIFFERENT WORKS (WITHIN Santoshpur zone-II AREA) RELATED TO CHILAKHANA PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000695/2024-2025 | 230/CD | 12/02/2025 | 13/04/2025 | M/S MM CONSTRUCTION | 9.06 | 0 | 0 | 100
12 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Santoshpur zone-II PWSS Accommodate FHTC in TFG-I Block . | SM/13382 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000026/2025-2026 | 714/CD | 17/05/2025 | 15/08/2025 | UTPAL CHAKRABORTY | 19.58 | 0 | 0 | 100
13 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Santoshpur zone-II PWSS Accommodate FHTC in TFG-I Block . | SM/13382 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000022/2025-2026 | 710/CD | 17/05/2025 | 13/11/2025 | UTTAM SAHA | 33.95 | 0 | 0 | 100
Total | [13 empty] | 586.42 | 229.21 | 39.09