## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Ground Water Based Piped Water Supply Scheme Bara Saulmari (Block-Mathabhanga-II) | SM/13383 | New | Providing House connection for BARO SOULMARI PWSS under Cooch Behar Division. PHE Dte | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000348/2021-2022 | 1249/CD | 09/02/2022 | 01/03/2022 | SHYAMAL NATH | 7.01 | 7.01 | 100 | 100
2 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Ground Water Based Piped Water Supply Scheme Bara Saulmari (Block-Mathabhanga-II) | SM/13383 | New | Execution of different works related to BARA SAULMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000117/2023-2024 | 620_/CD | 12/07/2023 | 09/12/2023 | SUMI ENTERPRISE | 481.49 | 155.81 | 32.36 | 28
3 | COOCHBEHAR | Mathabhanga-II | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme Bara Saulmari (Block-Mathabhanga-II) | SM/13383 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for BARA SAULMARI (Mathabhnga-II Block) water supply scheme, TW no I, II and III under Jal Jeevan Mission under NMD-II, PHE Dte. Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000872/2023-2024 | 2452/NMD-II | 11/08/2023 | 10/09/2023 | M/S B ENTERPRISE | 31.66 | 8.38 | 26.47 | 30
4 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Ground Water Based Piped Water Supply Scheme Bara Saulmari (Block-Mathabhanga-II) | SM/13383 | New | Providing FHTC and Laying of Pipe line & Construction Of Boundary Wall And Pump House At 3RD Site of BARO SOULMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000239/2022-2023 | 725/CD | 27/08/2022 | 11/10/2022 | SHYAMAL NATH | 62.93 | 61.87 | 98.32 | 55
5 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Ground Water Based Piped Water Supply Scheme Bara Saulmari (Block-Mathabhanga-II) | SM/13383 | New | Shifting of Water Pipeline form Ranirhat Tepathi to Soulmari High School due to Rd Widening of Jamaldah-Ranirhat PWD Road Crossing under Cooch Behar Division, PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000002/2022-2023 | 18/CD | 07/04/2022 | 06/06/2022 | NO 1 GURIAHATI CO OP LABOUR CONTRACT AND CONSTRUCT SOCY LTD | 25.89 | 0 | 0 | 100
6 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Ground Water Based Piped Water Supply Scheme Bara Saulmari (Block-Mathabhanga-II) | SM/13383 | New | Material Requisition To Resource Division |  |  | RTOR000190/2023-2024 | 69/CD | 11/01/2024 | 11/01/2024 | Resource Division | 16.05 | 0 | 0 | 0
7 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Ground Water Based Piped Water Supply Scheme Bara Saulmari (Block-Mathabhanga-II) | SM/13383 | New | quotation for new connection bara saulmari tw 3 |  |  | BILL/01313/2023-2024 | BP-1040 | 13/02/2024 | 13/02/2024 | WBSEDCL | 4.04 | 0 | 0 | 0
8 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Ground Water Based Piped Water Supply Scheme Bara Saulmari (Block-Mathabhanga-II) | SM/13383 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
9 | COOCHBEHAR | Mathabhanga-II | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme Bara Saulmari (Block-Mathabhanga-II) | SM/13383 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of CoochBehar District in West Bengal. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/000063/2025-2026 | 1156/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 488.07 | 0 | 0 | 0
10 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Ground Water Based Piped Water Supply Scheme Bara Saulmari (Block-Mathabhanga-II) | SM/13383 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000105/2025-2026 | 1425/CD | 11/08/2025 | 09/11/2025 | SENGUPTA ENTERPRISE | 42.84 | 0 | 0 | 0
11 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | Ground Water Based Piped Water Supply Scheme Bara Saulmari (Block-Mathabhanga-II) | SM/13383 | New | EXECUTION OF DIFFERENT WORKS RELATED TO BARA SOULMARI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000558/2024-2025 | 2243/CD | 23/12/2024 | 22/04/2025 | SHYAMAL NATH | 18.24 | 0 | 0 | 98
Total | [13 empty] | 20967.51 | 233.07 | 1.11