## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | Ground Water Based Piped Water Supply Scheme Bara Saulmari (Block-Mathabhanga-II) | SM/13383 | New | Providing House connection for BARO SOULMARI PWSS under Cooch Behar Division. PHE Dte | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000348/2021-2022 | 1249/CD | 09/02/2022 | 01/03/2022 | SHYAMAL NATH | 7.01 | 7.01 | 100 | 100
2 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | Ground Water Based Piped Water Supply Scheme Bara Saulmari (Block-Mathabhanga-II) | SM/13383 | New | Providing FHTC and Laying of Pipe line & Construction Of Boundary Wall And Pump House At 3RD Site of BARO SOULMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000239/2022-2023 | 725/CD | 27/08/2022 | 11/10/2022 | SHYAMAL NATH | 62.93 | 58.43 | 92.85 | 55
3 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | Ground Water Based Piped Water Supply Scheme Bara Saulmari (Block-Mathabhanga-II) | SM/13383 | New | Shifting of Water Pipeline form Ranirhat Tepathi to Soulmari High School due to Rd Widening of Jamaldah-Ranirhat PWD Road Crossing under Cooch Behar Division, PHED | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000002/2022-2023 | 18/CD | 07/04/2022 | 06/06/2022 | NO 1 GURIAHATI CO OP LABOUR CONTRACT AND CONSTRUCT SOCY LTD | 25.89 | 0 | 0 | 100
4 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | Ground Water Based Piped Water Supply Scheme Bara Saulmari (Block-Mathabhanga-II) | SM/13383 | New | Material Requisition To Resource Division |  |  | RTOR000190/2023-2024 | 69/CD | 11/01/2024 |  | Resource Division | 16.05 | 0 | 0 | 0
5 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | Ground Water Based Piped Water Supply Scheme Bara Saulmari (Block-Mathabhanga-II) | SM/13383 | New | Execution of different works related to BARA SAULMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000117/2023-2024 | 620_/CD | 12/07/2023 | 09/12/2023 | SUMI ENTERPRISE | 481.49 | 77.91 | 16.18 | 28
6 | COOCHBEHAR | Mathabhanga - II | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme Bara Saulmari (Block-Mathabhanga-II) | SM/13383 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for BARA SAULMARI (Mathabhnga-II Block) water supply scheme, TW no I, II and III under Jal Jeevan Mission under NMD-II, PHE Dte. Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000872/2023-2024 | 2452/NMD-II | 11/08/2023 | 10/09/2023 | M/S B ENTERPRISE | 31.66 | 4.19 | 13.24 | 30
7 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | Ground Water Based Piped Water Supply Scheme Bara Saulmari (Block-Mathabhanga-II) | SM/13383 | New | quotation for new connection bara saulmari tw 3 |  |  | BILL/01313/2023-2024 | BP-1040 | 13/02/2024 |  | WBSEDCL | 4.04 | 0 | 0 | 0
8 | COOCHBEHAR | Mathabhanga - II | Coochbehar Division | Ground Water Based Piped Water Supply Scheme Bara Saulmari (Block-Mathabhanga-II) | SM/13383 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
Total | [13 empty] | 20418.36 | 147.54 | 0.72