## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Santoshpur Zone-I PWSS Accommodate FHTC in TFG-I Block under Cooch Behar Division. | SM/13385 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000117/2023-2024 | 216/CD | 27/04/2023 | 27/04/2023 | Resource Division | 17.46 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Santoshpur Zone-I PWSS Accommodate FHTC in TFG-I Block under Cooch Behar Division. | SM/13385 | Augmentation | exc. of difft. work at atpukhari pwss |  |  | BILL/00791/2023-2024 | BP-250-P2 | 04/07/2023 | 04/07/2023 | MODERN UN-EMP CO-OPT LABOUR CONT & CONSTN SOCIETY LIMITED | 29.8 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Santoshpur Zone-I PWSS Accommodate FHTC in TFG-I Block under Cooch Behar Division. | SM/13385 | Augmentation | exc. of difft. works at ghughumari pwss |  |  | BILL/00789/2023-2024 | BP-243 | 01/07/2023 | 01/07/2023 | MS BIDYUT SARKAR | 30 | 0 | 0 | 0
4 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Santoshpur Zone-I PWSS Accommodate FHTC in TFG-I Block under Cooch Behar Division. | SM/13385 | Augmentation | New service connection charge at Santoshpur (Zone-I) PWSS, P/H-III. |  |  | BILL/00888/2024-2025 | BP-287/24-25 | 22/08/2024 | 22/08/2024 | WBSEDCL | 5.86 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Santoshpur Zone-I PWSS Accommodate FHTC in TFG-I Block under Cooch Behar Division. | SM/13385 | Augmentation | Execution of different works related to SANTOSHPUR ZONE-I PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1010/1-5/NBC-1; Dt.: 24-01-23 | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000496/2022-2023 | 1561/CD | 24/01/2023 | 12/02/2025 | UTPAL CHAKRABORTY | 265.78 | 0 | 0 | 20
6 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Santoshpur Zone-I PWSS Accommodate FHTC in TFG-I Block under Cooch Behar Division. | SM/13385 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Augmentation of Santoshpur water supply scheme, TW no III of Zone-I and TW No-III of Zone-II under Northern Mechanical Division-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000821/2023-2024 | 2399/NMD-II | 09/08/2023 | 08/09/2023 | P K ENGINEERING | 20.78 | 0 | 0 | 100
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Santoshpur Zone-I PWSS Accommodate FHTC in TFG-I Block under Cooch Behar Division. | SM/13385 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of Santoshpur Zone-I PWSS Accommodate FHTC in TFG-I Block under Cooch Behar Division. | SM/13385 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO SANTOSHPUR PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000542/2024-2025 | 2226/CD | 23/12/2024 | 21/02/2025 | UTPAL CHAKRABORTY | 41.33 | 0 | 0 | 20
9 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of Santoshpur Zone-I PWSS Accommodate FHTC in TFG-I Block under Cooch Behar Division. | SM/13385 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Santoshpur Water Supply Scheme TW No.- II of Zone- II under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/001225/2024-2025 | 845/NMD-II | 11/03/2025 | 10/04/2025 | D.K AND SONS | 10.41 | 0 | 0 | 80
Total | [13 empty] | 20210.71 | 0 | 0