## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | Augmentation of bajejama chilakhana zone-II PWSS | SM/13386 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000116/2023-2024 | 215/CD | 27/04/2023 | 27/04/2023 | Resource Division | 16.59 | 0 | 0 | 0
2 | COOCHBEHAR |  | Coochbehar Division | Augmentation of bajejama chilakhana zone-II PWSS | SM/13386 | Augmentation | Execution of different works related to B. CHILAKHANA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000174/2023-2024 | 951/CD | 04/09/2023 | 26/05/2025 | HARIDAS GHOSH | 35.71 | 23.53 | 65.87 | 100
3 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of bajejama chilakhana zone-II PWSS | SM/13386 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augmentation of Bajejama Chilakhana Water Supply Scheme TW No.- I & II of Zone-II under NMD-II,PHE.Dte,Apd. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/001177/2023-2024 | 2908/NMD-II | 31/10/2023 | 30/11/2023 | RAJEEV RANJAN OJHA | 20.47 | 0 | 0 | 50
4 | COOCHBEHAR |  | Coochbehar Division | Augmentation of bajejama chilakhana zone-II PWSS | SM/13386 | Augmentation | Execution of different works related to AUG. of BAJEJAMA CHILAKHANA ZONE-II PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1175/1-5/NBC-1; Dt.: 24-02-23 | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000621/2022-2023 | 1875/CD | 14/03/2023 | 07/03/2025 | NABIN DEBNATH | 288.17 | 200.27 | 69.5 | 10
5 | COOCHBEHAR |  | Coochbehar Division | Augmentation of bajejama chilakhana zone-II PWSS | SM/13386 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
6 | COOCHBEHAR |  | Coochbehar Division | Augmentation of bajejama chilakhana zone-II PWSS | SM/13386 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000034/2025-2026 | 719/CD | 17/05/2025 | 13/11/2025 | AASHIRBAD ENTERPRISE | 50.96 | 0 | 0 | 70
7 | COOCHBEHAR |  | Coochbehar Division | Augmentation of bajejama chilakhana zone-II PWSS | SM/13386 | Augmentation | EXECUTION OF DIFFERENT WORKS RELATED DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000054/2025-2026 | 602/CD | 28/04/2025 | 27/07/2025 | SSPR VALVE MANUFACTURING PVT. LTD. | 96.82 | 0 | 0 | 0
8 | COOCHBEHAR |  | Coochbehar Division | Augmentation of bajejama chilakhana zone-II PWSS | SM/13386 | Augmentation | HORDING/ SIGN BOARD FOR IEC CAMPAINING AT GP OFFICE / BLOCK OFFICE & DIFFERENT HEALTH CENTERS UNDER COOCH BEHAR DIVISION , PHE Dte | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000704/2024-2025 | 2326/CD | 23/12/2024 | 21/02/2025 | ISLAMPUR SWARNADEEP SOCIETY | 48.03 | 0 | 0 | 100
9 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of bajejama chilakhana zone-II PWSS | SM/13386 | Augmentation | Charges for new service connection at Bajejama Chilakhana PWSS (Zone-II) P/H-I in the dist of Coochbehar. |  |  | BILL/01576/2024-2025 | BP-420/24-25 | 20/11/2024 | 20/11/2024 | WBSEDCL | 10.57 | 0 | 0 | 0
10 | COOCHBEHAR |  | Northern Mechanical Division II | Augmentation of bajejama chilakhana zone-II PWSS | SM/13386 | Augmentation | Charges for new service connection at Bajejama Chilakhana (Zone-II) PWSS, P/H-II in the Dist of Coochbehar. |  |  | BILL/01526/2024-2025 | BP-419/24-25 | 20/11/2024 | 20/11/2024 | WBSEDCL | 10.41 | 0 | 0 | 0
Total | [13 empty] | 20367.02 | 223.79 | 1.1