## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DAKHSHIN DIGHALTARI PWSS | SM/13388 | New | Material Requisition To Resource Division |  |  | RTOR000069/2023-2024 | 152/CD | 27/04/2023 | 27/04/2023 | Resource Division | 22.01 | 0 | 0 | 0
2 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | DAKHSHIN DIGHALTARI PWSS | SM/13388 | New | QUOTATION FOR NSC AT DIGHALTARI PH NO I |  |  | BILL/02202/2023-2024 | BP-2023-24-456 | 07/12/2023 | 07/12/2023 | WBSEDCL | 3.06 | 0 | 0 | 0
3 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | DAKHSHIN DIGHALTARI PWSS | SM/13388 | New | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for DAKHSHIN DIGHALTARI water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte. Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000871/2023-2024 | 2451/NMD-II | 11/08/2023 | 10/09/2023 | HARAGOURI ENTERPRISE | 19.82 | 0 | 0 | 100
4 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | DAKHSHIN DIGHALTARI PWSS | SM/13388 | New | QUOTATION FOR NSC AT DIGHALTARI PH NO II |  |  | BILL/02195/2023-2024 | BP-2023-24-457 | 07/12/2023 | 07/12/2023 | WBSEDCL | 4.77 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DAKHSHIN DIGHALTARI PWSS | SM/13388 | New | Execution of different works related to DINHATA (P) & Adjacent Jarabari Pratham Khanda & Dakhshin Dighaltari PWSS under JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000084/2024-2025 | 1189/CD | 18/06/2024 | 01/11/2025 | M/S J C ENTERPRISE | 80.91 | 0 | 0 | 85
6 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DAKHSHIN DIGHALTARI PWSS | SM/13388 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000286/2025-2026 | 795/CD | 23/05/2025 | 19/11/2025 | NORTH BENGAL CONSTRUCTION CO | 37.91 | 0 | 0 | 30
7 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DAKHSHIN DIGHALTARI PWSS | SM/13388 | New | Execution of different works related to DAKHSHIN DIGHALTARI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1122/1-5/NBC-1; Dt.: 13-02-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000603/2022-2023 | 1855/CD | 14/03/2023 | 28/04/2025 | SANKAR CHAKRABORTY | 303.42 | 0 | 0 | 54
8 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DAKHSHIN DIGHALTARI PWSS | SM/13388 | New | Execution of different works related to DAKSHIN DIGHALTARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000422/2023-2024 | 1478/CD | 20/12/2023 | 20/04/2025 | SANKAR CHAKRABORTY | 53.8 | 0 | 0 | 90
Total | [13 empty] | 525.7 | 0 | 0