## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | GROUND WATER BASED BALASI PIPED WATER SUPPLY SCHEME. | SM/13389 | New | Material Requisition To Resource Division |  |  | RTOR000039/2022-2023 | 1343/CD | 19/12/2022 | 19/12/2022 | Resource Division | 61.6 | 0 | 0 | 0
2 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | GROUND WATER BASED BALASI PIPED WATER SUPPLY SCHEME. | SM/13389 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for of Balasi water supply scheme, TW no I and II under Northern Mechanical Division-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000681/2023-2024 | 2127/NMD-II | 27/07/2023 | 26/08/2023 | SUBODH KUMAR BANIK | 22.03 | 0 | 0 | 0
3 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | GROUND WATER BASED BALASI PIPED WATER SUPPLY SCHEME. | SM/13389 | New | Material Requisition To Resource Division |  |  | RTOR000082/2023-2024 | 178/CD | 27/04/2023 | 27/04/2023 | Resource Division | 44.89 | 0 | 0 | 0
4 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | GROUND WATER BASED BALASI PIPED WATER SUPPLY SCHEME. | SM/13389 | New | QUOTATION FOR NEW SERVICE CONNECTION AT BALASHI PWSS PH NO-II |  |  | BILL/00082/2023-2024 | BP-2023-24-77 | 15/05/2023 | 15/05/2023 | WBSEDCL | 0.93 | 0 | 0 | 0
5 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | GROUND WATER BASED BALASI PIPED WATER SUPPLY SCHEME. | SM/13389 | New | Material Requisition To Resource Division |  |  | RTOR000185/2023-2024 | 82/CD | 11/01/2024 | 11/01/2024 | Resource Division | 15.46 | 0 | 0 | 0
6 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | GROUND WATER BASED BALASI PIPED WATER SUPPLY SCHEME. | SM/13389 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BALASI TW I. |  |  | BILL/00519/2024-2025 | BP-122/24-25 | 24/05/2024 | 24/05/2024 | WBSEDCL | 6.55 | 0 | 0 | 0
7 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | GROUND WATER BASED BALASI PIPED WATER SUPPLY SCHEME. | SM/13389 | New | Execution of different works related to BALASI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1346/1-5/NBC-1; Dt.: 24-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000615/2022-2023 | 1965/CD | 24/03/2023 | 09/09/2025 | GHOSH AND SAHA CONSTRUCTION | 547.55 | 398.42 | 72.76 | 70
8 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | GROUND WATER BASED BALASI PIPED WATER SUPPLY SCHEME. | SM/13389 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
9 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | GROUND WATER BASED BALASI PIPED WATER SUPPLY SCHEME. | SM/13389 | New | Execution of different works (WITHIN BALASI AREA) related to KHENGCHI PWSS under JAL JEEVAN MISSION |  |  | ORD/000809/2023-2024 | 276/CD | 09/02/2024 | 09/04/2024 | ASHIM KUMAR CHAKRABORTY | 45.66 | 0 | 0 | 0
10 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | GROUND WATER BASED BALASI PIPED WATER SUPPLY SCHEME. | SM/13389 | New | EXECUTION OF DIFFERENT WORKS RELATED TO (within MARICHBARI, KHATERBARI & BALASI area) BHANGAMORE PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000651/2024-2025 | 2330/CD | 23/12/2024 | 21/02/2025 | SUPRITI ENTERPRISE | 89.52 | 0 | 0 | 0
11 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | GROUND WATER BASED BALASI PIPED WATER SUPPLY SCHEME. | SM/13389 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of CoochBehar District in West Bengal. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/000063/2025-2026 | 1156/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 488.07 | 0 | 0 | 0
12 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | GROUND WATER BASED BALASI PIPED WATER SUPPLY SCHEME. | SM/13389 | New | Yard lighting arrangement at Head Work Site for Different PWSS (BALASI and others) under JJM in the BLOCK: Mathabhanga-I, DISTRICT: Coochbehar under NMD-II,PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000139/2025-2026 | 1348/NMD-II | 19/06/2025 | 19/07/2025 | S.K ENTERPRISE | 34.38 | 0 | 0 | 0
13 | COOCHBEHAR | Mathabhanga-I | Coochbehar Division | GROUND WATER BASED BALASI PIPED WATER SUPPLY SCHEME. | SM/13389 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000075/2025-2026 | 752/CD | 17/05/2025 | 15/08/2025 | SHREE RANI SATI ENTERPRISE | 56.67 | 0 | 0 | 0
14 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | GROUND WATER BASED BALASI PIPED WATER SUPPLY SCHEME. | SM/13389 | New | ADDITIONAL ELECTRIC QUOTATION FOR CHANGE IN ROUTE AT BALASI TW I |  |  | BILL/02036/2024-2025 | BP-456/24-25 | 09/01/2025 | 09/01/2025 | WBSEDCL | 1.15 | 0 | 0 | 0
15 | COOCHBEHAR | Mathabhanga-I | Northern Mechanical Division II | GROUND WATER BASED BALASI PIPED WATER SUPPLY SCHEME. | SM/13389 | New | Solarization of grid connected pumping installation at Different PWSS at Mathabhanga-I Block in the dist.of Coochbehar under JJM programme under Northern Mechanical Division-II, PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000167/2025-2026 | 1388/NMD-II | 26/06/2025 | 24/09/2025 | E AND C ENGINEERING & CONSULTANCY SERVICES PRIVATE LIMITED | 47.89 | 0 | 0 | 30
Total | [13 empty] | 21251.64 | 398.42 | 1.87