## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | MOAMARI PIPED WATER SUPPLY SCHEME. | SM/13399 | New | Material Requisition To Resource Division |  |  | RTOR000145/2023-2024 | 253/CD | 27/04/2023 |  | Resource Division | 14.12 | 0 | 0 | 0
2 | COOCHBEHAR | Cooch Behar - I | Northern Mechanical Division II | MOAMARI PIPED WATER SUPPLY SCHEME. | SM/13399 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Moamari water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000979/2023-2024 | 2609/NMD-II | 25/08/2023 | 24/09/2023 | M/S CHANDRANATH MUKHERJEE | 19.82 | 7.98 | 40.25 | 50
3 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | MOAMARI PIPED WATER SUPPLY SCHEME. | SM/13399 | New | Execution of different works related to PANISALA & DWN MOAMARI PWSS under JAL JEEVAN MISSION |  |  | ORD/000042/2024-2025 | 1150/CD | 14/06/2024 | 13/08/2024 | GOUTAM KUMAR DAS | 23.64 | 0 | 0 | 0
4 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | MOAMARI PIPED WATER SUPPLY SCHEME. | SM/13399 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
5 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | MOAMARI PIPED WATER SUPPLY SCHEME. | SM/13399 | New | Execution of different works related to AUG. DEWANHAT PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000067/2024-2025 | 1324/CD | 19/07/2024 | 17/10/2024 | DAS ENTERPRISE | 45.49 | 0 | 0 | 0
6 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | MOAMARI PIPED WATER SUPPLY SCHEME. | SM/13399 | New | Execution of different works related to MOAMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000137/2023-2024 | 805/CD | 08/08/2023 | 05/01/2024 | SUDIPTA BOSE | 343.98 | 56.72 | 16.49 | 40
7 | COOCHBEHAR | Cooch Behar - I | Northern Mechanical Division II | MOAMARI PIPED WATER SUPPLY SCHEME. | SM/13399 | New | NEW SERVICE CONNECTION AT MOAMARI PWSS PH-I |  |  | BILL/01036/2024-2025 | BP-303/24-25 | 22/08/2024 |  | WBSEDCL | 9.23 | 0 | 0 | null
8 | COOCHBEHAR | Cooch Behar - I | Northern Mechanical Division II | MOAMARI PIPED WATER SUPPLY SCHEME. | SM/13399 | New | NEW SERVICE CONNECTION AT MOAMARI PWSS PH-I |  |  | BILL/01036/2024-2025 | BP-303/24-25 | 22/08/2024 |  | WBSEDCL | 9.23 | 0 | 0 | null
Total | [13 empty] | 20254.81 | 64.69 | 0.32