## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | Material Requisition To Resource Division |  |  | RTOR000009/2023-2024 | 96/CD | 26/04/2023 | 26/04/2023 | Resource Division | 16.87 | 0 | 0 | 0
2 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | QUOTATION FOR NSC AT MAYANAGURI DIGHALHATI TW NO-I |  |  | BILL/01795/2023-2024 | BP-2023-24-308 | 27/09/2023 | 27/09/2023 | WBSEDCL | 5.14 | 0 | 0 | 0
3 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | QUOTATION FOR NSC AT MAYANAGURI DIGHALHATI TW NO-II |  |  | BILL/01794/2023-2024 | BP-2023-24-309 | 27/09/2023 | 27/09/2023 | WBSEDCL | 8.21 | 0 | 0 | 0
4 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO MAINAGURI DIGHALATI PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000544/2024-2025 | 2228/CD | 23/12/2024 | 21/02/2025 | S. DUTTA | 33.43 | 0 | 0 | 0
5 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | Gap filling between pipe line related to Bhogdabri & M DIGHALHATI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000546/2023-2024 | 650/CD | 11/03/2024 | 10/05/2024 | M/S MAA MANASA CONSTRUCTION CO. | 17.68 | 17.44 | 98.64 | 35
6 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | ADDITIONAL QUOTATION FOR ELECTRICAL INFRA. DEV. WORK AT MAINAGURI DIGHALHATI. |  |  | BILL/00818/2024-2025 | BP-246/24-25 | 30/07/2024 | 30/07/2024 | WBSEDCL | 3.5 | 0 | 0 | 0
7 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000312/2025-2026 | 4052 | 18/08/2025 | 16/11/2025 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
8 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000313/2025-2026 | 4053 | 18/08/2025 | 16/11/2025 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
9 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000321/2025-2026 | 4061 | 18/08/2025 | 16/11/2025 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
10 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000322/2025-2026 | 4062 | 18/08/2025 | 16/11/2025 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
11 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000125/2025-2026 | a3 | 08/07/2025 | 06/10/2025 | ASHIM KUMAR CHAKRABORTY | 0 | 0 | NAN | 0
12 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000319/2025-2026 | 4059 | 18/08/2025 | 16/11/2025 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
13 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000293/2025-2026 | 4037 | 11/08/2025 | 09/11/2025 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
14 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000295/2025-2026 | 4039 | 11/08/2025 | 09/11/2025 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
15 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000308/2025-2026 | 4048 | 18/08/2025 | 16/11/2025 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
16 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000309/2025-2026 | 4049 | 18/08/2025 | 16/11/2025 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
17 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000311/2025-2026 | 4051 | 18/08/2025 | 16/11/2025 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
18 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000314/2025-2026 | 4054 | 18/08/2025 | 16/11/2025 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
19 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000317/2025-2026 | 4057 | 18/08/2025 | 16/11/2025 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
20 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000268/2025-2026 | 766/CD | 17/05/2025 | 15/08/2025 | SUBHAS CHANDRA ROY | 15.17 | 0 | 0 | 0
21 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000306/2025-2026 | 4046 | 18/08/2025 | 16/11/2025 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
22 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000304/2025-2026 | 4044 | 18/08/2025 | 16/11/2025 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
23 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000305/2025-2026 | 4045 | 18/08/2025 | 16/11/2025 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
24 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000307/2025-2026 | 4047 | 18/08/2025 | 16/11/2025 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
25 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000315/2025-2026 | 4055 | 18/08/2025 | 16/11/2025 | AASHIRBAD ENTERPRISE | 0 | 0 | NAN | 0
26 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000316/2025-2026 | 4056 | 18/08/2025 | 16/11/2025 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
27 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000320/2025-2026 | 4060 | 18/08/2025 | 16/11/2025 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
28 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000294/2025-2026 | 4038 | 11/08/2025 | 09/11/2025 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
29 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000318/2025-2026 | 4058 | 18/08/2025 | 16/11/2025 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
30 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000310/2025-2026 | 4050 | 18/08/2025 | 16/11/2025 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
31 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000298/2025-2026 | 4042 | 12/08/2025 | 10/11/2025 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
32 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000299/2025-2026 | 4043 | 12/08/2025 | 10/11/2025 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
33 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000065/2025-2026 | z1 | 05/07/2025 | 03/10/2025 | S. DUTTA | 47.93 | 0 | 0 | 0
34 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000296/2025-2026 | 4040 | 11/08/2025 | 09/11/2025 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
35 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000297/2025-2026 | 4041 | 11/08/2025 | 09/11/2025 | AASHIRBAD ENTERPRISE | 0 | 0 | 0 | 0
36 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | Execution of different works related to MAINAGURI DIGHALHATI PWSS under JAL JEEVAN MISSION SE NBC1/PHED A. O.: 982/1-5/NBC-1; DT: 19-01-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000462/2022-2023 | 1513/CD | 19/01/2023 | 13/06/2026 | S DUTTA | 489.9 | 342.37 | 69.88 | 60
37 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
38 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000084/2025-2026 | 730/CD | 17/05/2025 | 15/08/2025 | SSPR VALVE MANUFACTURING PVT. LTD. | 96.82 | 0 | 0 | 0
39 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000066/2025-2026 | 750/CD | 17/05/2025 | 15/08/2025 | S. DUTTA | 47.26 | 0 | 0 | 0
40 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | MAINAGURI DIGHALHATI PIPED WATER SUPPLY SCHEME. | SM/13400 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Mainaguri Dighalhati water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000759/2023-2024 | 2338/NMD-II | 01/08/2023 | 23/03/2025 | THE BANERJEE CONCERN | 22.1 | 19.52 | 88.3 | 100
Total | [13 empty] | 20593.31 | 379.32 | 1.84