## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata-I | Central Drilling | DINHATA(P) PIPED WATER SUPPLY SCHEME. | SM/13401 | New | PROVIDING STRAINER CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT DINHATA W/S SCH (TW-II) UNDER COOCHBEHAR DISTRICT, CDD, PHE DTE. |  |  | ORD/000240/2022-2023 | 240/CMSD-I | 20/06/2022 | 05/07/2022 | M/S SAIKAT ENTERPRISE | 2.21 | 2.19 | 98.75 | 0
2 | COOCHBEHAR | Dinhata-I | Central Drilling | DINHATA(P) PIPED WATER SUPPLY SCHEME. | SM/13401 | New | PROVIDING PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL AT DINHATA W/S (TW-II) UNDER COOCHBEHAR DISTRICT, CDD, PHE DTE. |  |  | ORD/000238/2022-2023 | 238/CMSD-I | 20/06/2022 | 05/07/2022 | PADMA ENGINEERING & CO. | 2.04 | 2.02 | 98.86 | 0
3 | COOCHBEHAR | Dinhata-I | Central Drilling | DINHATA(P) PIPED WATER SUPPLY SCHEME. | SM/13401 | New | PROVIDING HOUSING PIPE CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT DINHATA W/S SCH (TW-I), UNDER COOCHBEHAR DISTRICT, CDD, PHE DTE. |  |  | ORD/000235/2022-2023 | 235/CMSD-I | 20/06/2022 | 05/07/2022 | PADMA ENGINEERING & CO. | 2.81 | 2.63 | 93.9 | 0
4 | COOCHBEHAR | Dinhata-I | Central Drilling | DINHATA(P) PIPED WATER SUPPLY SCHEME. | SM/13401 | New | PROVIDING DRILLING CREW FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE FOR DINHATA W/S SCH (TW-II), UNDER COOCHBEHAR DISTRICT, CDD, PHE DTE. |  |  | ORD/000237/2022-2023 | 229/CMSD-I | 20/06/2022 | 05/07/2022 | M/S SAIKAT ENTERPRISE | 2.95 | 2.29 | 77.52 | 0
5 | COOCHBEHAR | Dinhata-I | Central Drilling | DINHATA(P) PIPED WATER SUPPLY SCHEME. | SM/13401 | New | PROVIDING PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL AT DINHATA W/S (TW-I), UNDER COOCHBEHAR DISTRICT, CDD, PHE DTE. |  |  | ORD/000232/2022-2023 | 245/CMSD-I | 20/06/2022 | 05/07/2022 | M/S SAIKAT ENTERPRISE | 2.04 | 2.04 | 99.94 | 0
6 | COOCHBEHAR | Dinhata-I | Central Drilling | DINHATA(P) PIPED WATER SUPPLY SCHEME. | SM/13401 | New | PROVIDING DRILLING CREW FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE FOR DINHATA W/S SCH (TW0I), UNDER COOCHBEHAR DISTRICT, CDD, PHE DTE. |  |  | ORD/000233/2022-2023 | 234/CMSD-I | 20/06/2022 | 05/07/2022 | PADMA ENGINEERING & CO. | 2.96 | 2.03 | 68.63 | 0
7 | COOCHBEHAR | Dinhata-I | Central Drilling | DINHATA(P) PIPED WATER SUPPLY SCHEME. | SM/13401 | New | PROVIDING STRAINER CONFORMING TO IS: 12818:2010 WITH OTHER MATYTERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT DINHATA W/S SCH, (TW-I) UNDER COOCHBEHAR DISTRICT, CDD, PHE DTE. |  |  | ORD/000234/2022-2023 | 236/CMSD-I | 20/06/2022 | 05/07/2022 | PADMA ENGINEERING & CO. | 2.22 | 2.22 | 99.93 | 0
8 | COOCHBEHAR | Dinhata-I | Central Drilling | DINHATA(P) PIPED WATER SUPPLY SCHEME. | SM/13401 | New | ADDITIONAL WORK FOR DRILLING BOLDER / SAND STONE ZONE DINHATA W/S SCH, TW-I UNDER COOCHBEHAR DISTRICT, CDD, PHE DTE. |  |  | ORD/000236/2022-2023 | 251/CMSD-I | 22/06/2022 | 07/07/2022 | PADMA ENGINEERING & CO. | 0.85 | 0.81 | 96 | 0
9 | COOCHBEHAR | Dinhata-I | Central Drilling | DINHATA(P) PIPED WATER SUPPLY SCHEME. | SM/13401 | New | PROVIDING HOUSING PIPE CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT DINHATA W/S SCH (TW-II) UNDER COOCHBEHAR DISTRICT, CDD, PHE DTE. |  |  | ORD/000239/2022-2023 | 239/CMSD-I | 20/06/2022 | 05/07/2022 | M/S SAIKAT ENTERPRISE | 2.8 | 2.71 | 96.95 | 0
10 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DINHATA(P) PIPED WATER SUPPLY SCHEME. | SM/13401 | New | Laying of Pipe Line between gap of different pin point site & other allied works under DINHATA (P) PWSS under Cooch Behar Division, PHE Dte. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000405/2023-2024 | 497/CD | 14/07/2023 | 12/09/2023 | HIRAK CONSTRUCTION | 9.99 | 0 | 0 | 0
11 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DINHATA(P) PIPED WATER SUPPLY SCHEME. | SM/13401 | New | Material Requisition To Resource Division |  |  | RTOR000066/2023-2024 | 175/CD | 27/04/2023 | 27/04/2023 | Resource Division | 37.69 | 0 | 0 | 0
12 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | DINHATA(P) PIPED WATER SUPPLY SCHEME. | SM/13401 | New | QUOTATION FOR NSC AT DINHATA (P) PUTIMARI PH NO I |  |  | BILL/01041/2023-2024 | BP-2023-24-238 | 27/07/2023 | 27/07/2023 | WBSEDCL | 8.98 | 0 | 0 | 0
13 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | DINHATA(P) PIPED WATER SUPPLY SCHEME. | SM/13401 | New | QUOTATION FOR NSC AT DINHATA (P) PYTIMARI |  |  | BILL/01040/2023-2024 | BP-2023-24-239 | 27/07/2023 | 27/07/2023 | WBSEDCL | 10.21 | 0 | 0 | 0
14 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | DINHATA(P) PIPED WATER SUPPLY SCHEME. | SM/13401 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Dinhata (P) water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte. APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000658/2023-2024 | 1964/NMD-II | 24/07/2023 | 23/08/2023 | M.S ENTERPRISE | 22.45 | 20.13 | 89.67 | 100
15 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DINHATA(P) PIPED WATER SUPPLY SCHEME. | SM/13401 | New | Laying of Pipe Line between gap of different pin point site & other allied works under DINHATA (M) PWSS under Cooch Behar Division, PHE Dte. P2 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000414/2023-2024 | 499/CD | 14/07/2023 | 12/09/2023 | HIRAK CONSTRUCTION | 4.99 | 4.99 | 99.99 | 95
16 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DINHATA(P) PIPED WATER SUPPLY SCHEME. | SM/13401 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Mekhliganj, Dinhata(P) Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000540/2023-2024 | 376/CD | 27/02/2024 | 27/04/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
17 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DINHATA(P) PIPED WATER SUPPLY SCHEME. | SM/13401 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Haldibari, Dinhata(P) Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000543/2023-2024 | 377/CD | 27/02/2024 | 27/04/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
18 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DINHATA(P) PIPED WATER SUPPLY SCHEME. | SM/13401 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Sitalkuchi, Dinhata(P) Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000535/2023-2024 | 373/CD | 27/02/2024 | 27/04/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
19 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DINHATA(P) PIPED WATER SUPPLY SCHEME. | SM/13401 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Dinhata-I, Dinhata(P) Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000532/2023-2024 | 366/CD | 22/02/2024 | 22/04/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
20 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DINHATA(P) PIPED WATER SUPPLY SCHEME. | SM/13401 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Dinhata-II, Dinhata(P) Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000533/2023-2024 | 367/CD | 22/02/2024 | 22/04/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
21 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DINHATA(P) PIPED WATER SUPPLY SCHEME. | SM/13401 | New | Extension work for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference of Sitai, Dinhata(P) Water Supply Scheme under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | Junior Engineer, Head Quarter | ORD/000534/2023-2024 | 372/CD | 27/02/2024 | 27/04/2024 | BIPASHA MAHANTA BANIK | 0.98 | 0.98 | 100 | 100
22 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DINHATA(P) PIPED WATER SUPPLY SCHEME. | SM/13401 | New | Material Requisition To Resource Division |  |  | RTOR000176/2023-2024 | 73/CD | 11/01/2024 | 11/01/2024 | Resource Division | 12.28 | 0 | 0 | 0
23 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DINHATA(P) PIPED WATER SUPPLY SCHEME. | SM/13401 | New | HIRING VEWHICLE FOR AE HQ |  |  | BILL/00596/2024-2025 | BP-231 | 01/08/2024 | 01/08/2024 | BHAGWATI BHUJEL | 0.77 | 0 | 0 | 0
24 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DINHATA(P) PIPED WATER SUPPLY SCHEME. | SM/13401 | New | FUEL BILL |  |  | BILL/02024/2023-2024 |  | 01/03/2024 | 01/03/2024 | A.O BSNL | 1.52 | 0 | 0 | 0
25 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DINHATA(P) PIPED WATER SUPPLY SCHEME. | SM/13401 | New | Execution of different works related to DINHATA (P) PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1054/1-5/NBC-1; Dt.: 03-02-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000598/2022-2023 | 1613/CD | 03/02/2023 | 30/09/2025 | M/S J C ENTERPRISE | 371.2 | 325.36 | 87.65 | 85
26 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DINHATA(P) PIPED WATER SUPPLY SCHEME. | SM/13401 | New | Execution of different works related to DINHATA (P) & Adjacent Jarabari Pratham Khanda & Dakhshin Dighaltari PWSS under JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000084/2024-2025 | 1189/CD | 18/06/2024 | 01/11/2025 | M/S J C ENTERPRISE | 80.91 | 7.39 | 9.14 | 85
27 | COOCHBEHAR | Dinhata-I | Coochbehar Division | DINHATA(P) PIPED WATER SUPPLY SCHEME. | SM/13401 | New | EXECUTION OF DIFFERENT WORKS RELATED TO (WITHIN DAKSHIN ALOKJHARI MEKHLIGANJ Block AREA) DINHATA (P) PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000607/2024-2025 | 2308/CD | 23/12/2024 | 29/10/2025 | M/S J C ENTERPRISE | 26.65 | 0 | 0 | 75
Total | [13 empty] | 614.44 | 382.73 | 62.29