## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | Providing FHTC and Laying of Pipe line & other allied works at lab building of AUG. of KHAGRABARI PWSS under JAL JEEVAN MISSION (Part-A) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000344/2022-2023 | 997/CD | 29/09/2022 | 28/11/2022 | DAS ENTERPRISE | 17.44 | 17.38 | 99.65 | 1
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | Providing FHTC and Laying of Pipe line & other allied works at lab building of AUG. of KHAGRABARI PWSS under JAL JEEVAN MISSION (Part-B) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000425/2022-2023 | 1104/CD | 21/10/2022 | 20/12/2022 | BIJOY ROY | 14.23 | 14.23 | 100 | 1
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | FHTC AT KHAGRABARI PWSS |  |  | VCH/001036/2022-2023 | 427 | 30/11/2022 | 30/11/2022 | RAJANI KANTA RAY | 4.83 | 0 | 0 | 0
4 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | FHTC AND OTHER ALLIED WORKS ETC. AT AUG. OF KHAGRABARI PWSS |  |  | VCH/001029/2022-2023 | 419 | 14/11/2022 | 14/11/2022 | BIJOY ROY | 14.87 | 0 | 0 | 0
5 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | Execution of different works related to KHAGRABARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000781/2022-2023 | 1697/CD | 13/02/2023 | 05/03/2023 | GOUTAM KUMAR DAS | 8.6 | 8.6 | 100 | 100
6 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | Training for improvement of Skillness of Pump Operator & Valve Operator of different PWSS of Cooch Behar-II Block held at Khagrabari under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000835/2022-2023 | 1617/CD/B | 03/02/2023 | 10/02/2023 | SWAPAN KR.SARKAR | 0.4 | 0 | 0 | 100
7 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | Execution of different works related to KHAGRABARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000796/2022-2023 | 1846/CD | 14/03/2023 | 13/04/2023 | BIJOY ROY | 3.71 | 3.46 | 93.41 | 100
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | Execution of different works related to KHAGRABARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000032/2023-2024 | 378/CD | 23/05/2023 | 22/07/2023 | MS SSB CONSTRUCTION CO | 64.14 | 64.07 | 99.89 | 95
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2023-2024 | 137/CD | 27/04/2023 | 27/04/2023 | Resource Division | 59.84 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | Execution of different works related to KHAGRABARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000444/2022-2023 | 1421/CD | 29/12/2022 | 28/01/2023 | SUBHAJIT DUTTA | 9.97 | 9.07 | 90.91 | 50
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | Execution of different works related to KHAGRABARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000789/2022-2023 | 1865/CD | 14/03/2023 | 13/04/2023 | RAJANI KANTA RAY | 21.94 | 21.32 | 97.2 | 100
12 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | Training for improvement of Skillness of Pump Operator & Valve Operator of different PWSS of Dinhata-II Block held at Gosanimari under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,Junior Engineer, Head Quarter | ORD/000836/2022-2023 | 1617/CD/C | 03/02/2023 | 10/02/2023 | SWAPAN KR.SARKAR | 0.54 | 0 | 0 | 100
13 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | Training for improvement of Skillness of Pump Operator & Valve Operator of different PWSS of Cooch Behar-I Block held at Dhaluabari under Cooch Behar Division, PHED. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000834/2022-2023 | 1617/CD/A | 03/02/2023 | 10/02/2023 | SWAPAN KR.SARKAR | 0.4 | 0.4 | 100 | 100
14 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | Execution of different works related to KHAGRABARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000077/2023-2024 | 433/CD | 29/05/2023 | 28/07/2023 | DAS ENTERPRISE | 9.16 | 8.4 | 91.77 | 80
15 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | Execution of different works related to KHAGRABARI Z PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000065/2024-2025 | 1272/CD | 03/07/2024 | 01/10/2024 | BILTU DAS | 84.91 | 53.38 | 62.87 | 70
16 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | Execution of different works related to KHAGRABARI PWSS under JAL JEEVAN MISSION Z3 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000052/2024-2025 | 1270/CD | 02/07/2024 | 30/09/2024 | BILTU DAS | 96.48 | 36.59 | 37.92 | 80
17 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2024-2025 | 1545/CD | 16/08/2024 | 16/08/2024 | Resource Division | 49.67 | 0 | 0 | 0
18 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | HIRING VEHICLE |  |  | BILL/00480/2024-2025 | BP-212 | 31/07/2024 | 31/07/2024 | BHAGWATI BHUJEL | 0.66 | 0 | 0 | 0
19 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | FHCT AT KHAGRABARI PWSS |  |  | BILL/01446/2023-2024 | BP-875-P | 12/01/2024 | 12/01/2024 | BIJOY ROY | 0.59 | 0 | 0 | 0
20 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
21 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | NEW SERVICE CONNECTION AT KHAGRABARI ZONE-IV, PH-I |  |  | BILL/03029/2023-2024 | BP-2023-24-683 | 14/03/2024 | 14/03/2024 | WBSEDCL | 6.59 | 0 | 0 | 0
22 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | Providing FHTC and Laying of Pipe line & other allied works at lab building of AUG. of KHAGRABARI PWSS under JAL JEEVAN MISSION (Part-C) | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000349/2022-2023 | 1002/CD | 29/09/2022 | 29/10/2022 | AASHIRBAD ENTERPRISE | 16.24 | 11.46 | 70.55 | 100
23 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | Execution of different works related to KHAGRABARI Z2 PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1107/1-5/NBC-1; Dt.: 13-02-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000589/2022-2023 | 1675/CD | 13/02/2023 | 03/01/2026 | MESSRS A.B.G CONSTRUCTION | 467.31 | 170.2 | 36.42 | 37
24 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | Execution of different works related to KHAGRABARI Z3 PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1343/1-5/NBC-1; Dt.: 24-03-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000597/2022-2023 | 1966/CD | 24/03/2023 | 04/09/2025 | MESSRS A.B.G CONSTRUCTION | 567.88 | 182.89 | 32.21 | 40
25 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | Execution of different works related to KHAGRABARI Z4 PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1005/1-5/NBC-1; Dt.: 24-01-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000501/2022-2023 | 1566/CD | 24/01/2023 | 31/08/2025 | M/S T R PARIK | 477.24 | 184.44 | 38.65 | 40
26 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for AUGUMENTATION OF KHAGRABARI Water Supply Scheme TW No.- I OF ZONE -I TW No.- I and II OF ZONE -II TW No.- I ,II AND III OF ZONE -III TW No.- I and II OF ZONE -IV under NMD-II,PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000901/2023-2024 | 2482/NMD-II | 11/08/2023 | 10/09/2023 | ALPHA ENTERPRISE | 89.84 | 0 | 0 | 15
27 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | Execution of different works related to KHAGRABARI Z1 PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000521/2022-2023 | 1608/CD | 03/02/2023 | 10/09/2025 | M/S T R PARIK | 440.06 | 177.81 | 40.41 | 30
28 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | NEW SERVICE CONNECTION AT KHARGRABARI Z-III, PH-I |  |  | BILL/02160/2024-2025 | BP-465/24-25 | 21/01/2025 | 21/01/2025 | WBSEDCL | 4.99 | 0 | 0 | 0
29 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | NEW SERVICE CONNECTION AT KHAGRABARI Z-III, PH-II |  |  | BILL/02161/2024-2025 | BP-464/24-25 | 21/01/2025 | 21/01/2025 | WBSEDCL | 4.74 | 0 | 0 | 0
30 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | NEW SERVICE CONNECTION CHARGES AT KHAGRABARI (AUG) PWSS , ZONE-I, PH-I |  |  | BILL/00356/2025-2026 |  | 07/05/2025 | 07/05/2025 | WBSEDCL | 8.98 | 0 | 0 | 0
31 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | NEW SERVICE CONNECTION AT KHAGRABARI Z-II, PH-I |  |  | BILL/02164/2024-2025 |  | 09/01/2025 | 09/01/2025 | WBSEDCL | 13.96 | 0 | 0 | 0
32 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF KHAGRABARI PIPED WATER SUPPLY SCHEME. | SM/13403 | Augmentation | NEW SERVICE CONNECTION AT KHAGRABARI ZONE-II PH-II |  |  | BILL/02162/2024-2025 |  | 09/01/2025 | 09/01/2025 | WBSEDCL | 7.47 | 0 | 0 | 0
Total | [13 empty] | 2623.39 | 963.7 | 36.74