## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Sitai | Coochbehar Division | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | Material Requisition To Resource Division |  |  | RTOR000034/2023-2024 | 131/CD | 27/04/2023 | 27/04/2023 | Resource Division | 16.7 | 0 | 0 | 0
2 | COOCHBEHAR | Sitai | Coochbehar Division | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | Execution of different works related to GABUA PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 160/1-5/NBC-1; Dt.: 18-05-23 | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, COOCHBEHAR DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000013/2023-2024 | 398/CD | 23/05/2023 | 20/10/2023 | UMEX POLYMERS PVT LTD | 405.33 | 370.58 | 91.43 | 95
3 | COOCHBEHAR | Sitai | Coochbehar Division | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | Execution of different works related to GABUA PWSS under JAL JEEVAN MISSION | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000544/2023-2024 | 638/CD | 11/03/2024 | 10/05/2024 | GOUTAM KUMAR DAS | 66.04 | 49.13 | 74.4 | 40
4 | COOCHBEHAR | Sitai | Northern Mechanical Division II | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for GABUA water supply scheme, TW no I and II under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001088/2023-2024 | 2788/NMD-II | 06/10/2023 | 05/11/2023 | M/S B ENTERPRISE | 19.45 | 5.42 | 27.89 | 100
5 | COOCHBEHAR | Sitai | Coochbehar Division | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | Designing, Making & erecting of DB using logo tagline for Cooch Behar districts under Jal Jeevan Mission (JJM) Support Activities Part F | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000583/2023-2024 | 622/CD | 11/03/2024 | 10/05/2024 | LIMRA SOCIAL WELFARE SOCIETY | 10.39 | 10.39 | 99.94 | 100
6 | COOCHBEHAR | Sitai | Coochbehar Division | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | shifting of LTOH LINE AT GABUA PWS SITAI CCC |  |  | BILL/00097/2024-2025 | BP-88 | 12/06/2024 | 12/06/2024 | WBSEDCL | 0.47 | 0 | 0 | 0
7 | COOCHBEHAR | Sitai | Northern Mechanical Division II | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT GABUA TW NO. I |  |  | BILL/02621/2023-2024 | BP-2023-24-581 | 01/02/2024 | 01/02/2024 | WBSEDCL | 6.84 | 0 | 0 | 0
8 | COOCHBEHAR | Sitai | Northern Mechanical Division II | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT GABUA TW NO. II. |  |  | BILL/02614/2023-2024 | BP-2023-24-577 | 01/02/2024 | 01/02/2024 | WBSEDCL | 4.93 | 0 | 0 | 0
9 | COOCHBEHAR | Sitai | Coochbehar Division | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
10 | COOCHBEHAR | Sitai | Coochbehar Division | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | Hiring of Diesel Vehicle for TFG Assistant Engineer for inspection of site checking of FHTC and LDS, searching of land for different PWSS under Cooch Behar Division, PHE Dte. (From 01-07-24 to 30-06-2025). |  |  | ORD/000466/2024-2025 | 1238/CD | 29/06/2024 | 29/06/2025 | GOUTAM KUMAR DAS | 1.92 | 0 | 0 | 0
11 | COOCHBEHAR | Sitai | Northern Mechanical Division II | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of CoochBehar District in West Bengal. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/000063/2025-2026 | 1156/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 488.07 | 0 | 0 | 0
12 | COOCHBEHAR | Sitai | Northern Mechanical Division II | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | Supply & delivery of actuator operated butterfly valve at GABUA W/S Scheme & adjacent sites in the district of Coochbehar within Coochbehar Mechanical Sub-division under Northern Mechanical Division-II P.H.E Dte. |  | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001204/2024-2025 | 281/CMSD | 06/03/2025 | 21/03/2025 | M/S B ENTERPRISE | 1.97 | 0 | 0 | 0
13 | COOCHBEHAR | Sitai | Coochbehar Division | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000017/2025-2026 | 702/CD | 17/05/2025 | 13/11/2025 | UMEX POLYMERS PVT LTD | 37.04 | 0 | 0 | 60
14 | COOCHBEHAR | Sitai | Northern Mechanical Division II | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | Solarization of grid connected pumping installation at Different PWSS at Sitai,Mathabanga and Mekhliganj Block in the dist.of Coochbehar under JJM programme under Northern Mechanical Division-II, PHE Dte | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000135/2025-2026 | 1335/NMD-II | 18/06/2025 | 16/09/2025 | M R S ELECTRICAL | 21.84 | 0 | 0 | 0
Total | [13 empty] | 20870.27 | 435.53 | 2.09