## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Sitai | Coochbehar Division | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | Material Requisition To Resource Division |  |  | RTOR000034/2023-2024 | 131/CD | 27/04/2023 |  | Resource Division | 16.7 | 0 | 0 | 0
2 | COOCHBEHAR | Sitai | Northern Mechanical Division II | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT GABUA TW NO. II. |  |  | BILL/02614/2023-2024 | BP-2023-24-577 | 01/02/2024 |  | WBSEDCL | 4.93 | 0 | 0 | null
3 | COOCHBEHAR | Sitai | Northern Mechanical Division II | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT GABUA TW NO. II. |  |  | BILL/02614/2023-2024 | BP-2023-24-577 | 01/02/2024 |  | WBSEDCL | 4.93 | 0 | 0 | null
4 | COOCHBEHAR | Sitai | Northern Mechanical Division II | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT GABUA TW NO. I |  |  | BILL/02621/2023-2024 | BP-2023-24-581 | 01/02/2024 |  | WBSEDCL | 6.84 | 0 | 0 | null
5 | COOCHBEHAR | Sitai | Northern Mechanical Division II | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT GABUA TW NO. I |  |  | BILL/02621/2023-2024 | BP-2023-24-581 | 01/02/2024 |  | WBSEDCL | 6.84 | 0 | 0 | null
6 | COOCHBEHAR | Sitai | Northern Mechanical Division II | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for GABUA water supply scheme, TW no I and II under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001088/2023-2024 | 2788/NMD-II | 06/10/2023 | 05/11/2023 | M/S B ENTERPRISE | 19.45 | 2.71 | 13.95 | 40
7 | COOCHBEHAR | Sitai | Coochbehar Division | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | Execution of different works related to GABUA PWSS under JAL JEEVAN MISSION | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR DIVISION | ORD/000544/2023-2024 | 638/CD | 11/03/2024 | 10/05/2024 | GOUTAM KUMAR DAS | 66.04 | 0 | 0 | 40
8 | COOCHBEHAR | Sitai | Coochbehar Division | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | Designing, Making & erecting of DB using logo tagline for Cooch Behar districts under Jal Jeevan Mission (JJM) Support Activities Part F | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000583/2023-2024 | 622/CD | 11/03/2024 | 10/05/2024 | LIMRA SOCIAL WELFARE SOCIETY | 10.39 | 0 | 0 | 100
9 | COOCHBEHAR | Sitai | Coochbehar Division | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | Execution of different works related to GABUA PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 160/1-5/NBC-1; Dt.: 18-05-23 | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, COOCHBEHAR DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000013/2023-2024 | 398/CD | 23/05/2023 | 20/10/2023 | UMEX POLYMERS PVT LTD | 405.33 | 208.47 | 51.43 | 68
10 | COOCHBEHAR | Sitai | Coochbehar Division | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
11 | COOCHBEHAR | Sitai | Coochbehar Division | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | shifting of LTOH LINE AT GABUA PWS SITAI CCC |  |  | BILL/00097/2024-2025 | BP-88 | 12/06/2024 |  | WBSEDCL | 0.47 | 0 | 0 | 0
12 | COOCHBEHAR | Sitai | Coochbehar Division | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | shifting of LTOH LINE AT GABUA PWS SITAI CCC |  |  | BILL/00097/2024-2025 | BP-88 | 12/06/2024 |  | WBSEDCL | 0.47 | 0 | 0 | 0
Total | [13 empty] | 20331.68 | 211.18 | 1.04