## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Sitai | Coochbehar Division | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | Material Requisition To Resource Division |  |  | RTOR000034/2023-2024 | 131/CD | 27/04/2023 | 27/04/2023 | Resource Division | 16.7 | 0 | 0 | 0
2 | COOCHBEHAR | Sitai | Coochbehar Division | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | Execution of different works related to GABUA PWSS under JAL JEEVAN MISSION | ADDITIONAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000544/2023-2024 | 638/CD | 11/03/2024 | 10/05/2024 | GOUTAM KUMAR DAS | 66.04 | 0 | 0 | 40
3 | COOCHBEHAR | Sitai | Northern Mechanical Division II | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for GABUA water supply scheme, TW no I and II under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001088/2023-2024 | 2788/NMD-II | 06/10/2023 | 05/11/2023 | M/S B ENTERPRISE | 19.45 | 0 | 0 | 100
4 | COOCHBEHAR | Sitai | Coochbehar Division | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | Designing, Making & erecting of DB using logo tagline for Cooch Behar districts under Jal Jeevan Mission (JJM) Support Activities Part F | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000583/2023-2024 | 622/CD | 11/03/2024 | 10/05/2024 | LIMRA SOCIAL WELFARE SOCIETY | 10.39 | 0 | 0 | 100
5 | COOCHBEHAR | Sitai | Coochbehar Division | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | shifting of LTOH LINE AT GABUA PWS SITAI CCC |  |  | BILL/00097/2024-2025 | BP-88 | 12/06/2024 | 12/06/2024 | WBSEDCL | 0.47 | 0 | 0 | 0
6 | COOCHBEHAR | Sitai | Northern Mechanical Division II | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT GABUA TW NO. I |  |  | BILL/02621/2023-2024 | BP-2023-24-581 | 01/02/2024 | 01/02/2024 | WBSEDCL | 6.84 | 0 | 0 | 0
7 | COOCHBEHAR | Sitai | Northern Mechanical Division II | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT GABUA TW NO. II. |  |  | BILL/02614/2023-2024 | BP-2023-24-577 | 01/02/2024 | 01/02/2024 | WBSEDCL | 4.93 | 0 | 0 | 0
8 | COOCHBEHAR | Sitai | Coochbehar Division | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
9 | COOCHBEHAR | Sitai | Northern Mechanical Division II | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of CoochBehar District in West Bengal. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/000063/2025-2026 | 1156/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 488.07 | 0 | 0 | 0
10 | COOCHBEHAR | Sitai | Coochbehar Division | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000017/2025-2026 | 702/CD | 17/05/2025 | 13/11/2025 | UMEX POLYMERS PVT LTD | 37.04 | 0 | 0 | 60
11 | COOCHBEHAR | Sitai | Northern Mechanical Division II | GABUA PIPED WATER SUPPLY SCHEME | SM/13458 | New | Solarization of grid connected pumping installation at Different PWSS at Sitai,Mathabanga and Mekhliganj Block in the dist.of Coochbehar under JJM programme under Northern Mechanical Division-II, PHE Dte | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000135/2025-2026 | 1335/NMD-II | 18/06/2025 | 16/09/2025 | M R S ELECTRICAL | 21.84 | 0 | 0 | 0
Total | [13 empty] | 20461.05 | 0 | 0