## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mekliganj | Northern Mechanical Division II | Ground water based Piped Water Supply Scheme DAKSHIN ALOKJHARI MEKHLIGANJ Block | SM/13459 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DAKHSHIN ALOKJHARI water supply scheme, TW no I and II under Northern Mechanical Division-II, PHE Dte. Alipurduar | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000670/2023-2024 | 2002/NMD-II | 25/07/2023 | 24/08/2023 | MASSK ENGINEERING WORKS | 21.02 | 0 | 0 | 0
2 | COOCHBEHAR | Mekliganj | Northern Mechanical Division II | Ground water based Piped Water Supply Scheme DAKSHIN ALOKJHARI MEKHLIGANJ Block | SM/13459 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Dakshin Alokjhari MEKHLIGANJ BLOCK Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000731/2023-2024 | 2229/NMD-II | 28/07/2023 | 27/08/2023 | SUNLIT | 21.01 | 0 | 0 | 0
3 | COOCHBEHAR | Mekliganj | Northern Mechanical Division II | Ground water based Piped Water Supply Scheme DAKSHIN ALOKJHARI MEKHLIGANJ Block | SM/13459 | New | QUOTATION FOR NSC AT ALOKJHARI TW NO II |  |  | BILL/01729/2023-2024 | BP-2023-24-315 | 27/09/2023 |  | WBSEDCL | 7.29 | 0 | 0 | 0
4 | COOCHBEHAR | Mekliganj | Coochbehar Division | Ground water based Piped Water Supply Scheme DAKSHIN ALOKJHARI MEKHLIGANJ Block | SM/13459 | New | Execution of different works related to DAKSHIN ALOKJHARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000323/2023-2024 | 1306/CD | 24/11/2023 | 23/01/2024 | MANABENDRA DE | 2.48 | 0 | 0 | 0
5 | COOCHBEHAR | Mekliganj | Coochbehar Division | Ground water based Piped Water Supply Scheme DAKSHIN ALOKJHARI MEKHLIGANJ Block | SM/13459 | New | Execution of different works related to DAKSHIN ALOKJHARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000556/2022-2023 | 1701/CD | 13/02/2023 | 13/07/2023 | ASHIT KUMAR SINGHA | 313.06 | 192.78 | 61.58 | 52
6 | COOCHBEHAR | Mekliganj | Coochbehar Division | Ground water based Piped Water Supply Scheme DAKSHIN ALOKJHARI MEKHLIGANJ Block | SM/13459 | New | Execution of different works related to DAKSHIN ALOKJHARI PWSS under JAL JEEVAN MISSION |  |  | ORD/000473/2023-2024 | 275/CD | 09/02/2024 | 09/04/2024 | ASHIT KUMAR SINGHA | 92.02 | 0 | 0 | 55
7 | COOCHBEHAR | Mekliganj | Coochbehar Division | Ground water based Piped Water Supply Scheme DAKSHIN ALOKJHARI MEKHLIGANJ Block | SM/13459 | New | EXECUTION OF DIFFERENT WORK AT DAKSHIN ALOKJJHARI PWSS |  |  | BILL/01963/2023-2024 | BP-1072 | 21/02/2024 |  | ASHIT KUMAR SINGHA | 2.24 | 0 | 0 | 0
8 | COOCHBEHAR | Mekliganj | Coochbehar Division | Ground water based Piped Water Supply Scheme DAKSHIN ALOKJHARI MEKHLIGANJ Block | SM/13459 | New | EXECUTION OF DIFFERENT WORK AT SHALBARI ZONE-IIN PWSS |  |  | BILL/02040/2023-2024 | BP-999 | 03/02/2024 |  | M/S B PAUL AND COMPANY | 47.55 | 0 | 0 | 0
9 | COOCHBEHAR | Mekliganj | Coochbehar Division | Ground water based Piped Water Supply Scheme DAKSHIN ALOKJHARI MEKHLIGANJ Block | SM/13459 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
Total | [13 empty] | 20295.96 | 192.78 | 0.95