## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mekliganj | Northern Mechanical Division II | Ground water based Piped Water Supply Scheme DAKSHIN ALOKJHARI MEKHLIGANJ Block | SM/13459 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Dakshin Alokjhari MEKHLIGANJ BLOCK Water Supply Scheme TW No.-I and II under NMD-II,PHE.Dte,Apd. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000731/2023-2024 | 2229/NMD-II | 28/07/2023 | 01/05/2025 | SUNLIT | 21.01 | 0 | 0 | 70
2 | COOCHBEHAR | Mekliganj | Northern Mechanical Division II | Ground water based Piped Water Supply Scheme DAKSHIN ALOKJHARI MEKHLIGANJ Block | SM/13459 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DAKHSHIN ALOKJHARI water supply scheme, TW no I and II under Northern Mechanical Division-II, PHE Dte. Alipurduar | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000670/2023-2024 | 2002/NMD-II | 25/07/2023 | 24/08/2023 | MASSK ENGINEERING WORKS | 21.02 | 0 | 0 | 0
3 | COOCHBEHAR | Mekliganj | Coochbehar Division | Ground water based Piped Water Supply Scheme DAKSHIN ALOKJHARI MEKHLIGANJ Block | SM/13459 | New | Execution of different works related to DAKSHIN ALOKJHARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000556/2022-2023 | 1701/CD | 13/02/2023 | 09/09/2025 | ASHIT KUMAR SINGHA | 313.06 | 226.27 | 72.28 | 52
4 | COOCHBEHAR | Mekliganj | Coochbehar Division | Ground water based Piped Water Supply Scheme DAKSHIN ALOKJHARI MEKHLIGANJ Block | SM/13459 | New | Execution of different works related to DAKSHIN ALOKJHARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000323/2023-2024 | 1306/CD | 24/11/2023 | 17/05/2025 | MANABENDRA DE | 2.48 | 0 | 0 | 50
5 | COOCHBEHAR | Mekliganj | Northern Mechanical Division II | Ground water based Piped Water Supply Scheme DAKSHIN ALOKJHARI MEKHLIGANJ Block | SM/13459 | New | QUOTATION FOR NSC AT ALOKJHARI TW NO II |  |  | BILL/01729/2023-2024 | BP-2023-24-315 | 27/09/2023 | 27/09/2023 | WBSEDCL | 7.29 | 0 | 0 | 0
6 | COOCHBEHAR | Mekliganj | Coochbehar Division | Ground water based Piped Water Supply Scheme DAKSHIN ALOKJHARI MEKHLIGANJ Block | SM/13459 | New | Execution of different works related to DAKSHIN ALOKJHARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000473/2023-2024 | 275/CD | 09/02/2024 | 08/04/2026 | ASHIT KUMAR SINGHA | 92.02 | 50.74 | 55.14 | 55
7 | COOCHBEHAR | Mekliganj | Coochbehar Division | Ground water based Piped Water Supply Scheme DAKSHIN ALOKJHARI MEKHLIGANJ Block | SM/13459 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
8 | COOCHBEHAR | Mekliganj | Coochbehar Division | Ground water based Piped Water Supply Scheme DAKSHIN ALOKJHARI MEKHLIGANJ Block | SM/13459 | New | EXECUTION OF DIFFERENT WORKS RELATED TO (WITHIN DAKSHIN ALOKJHARI MEKHLIGANJ Block AREA) DINHATA (P) PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000607/2024-2025 | 2308/CD | 23/12/2024 | 25/08/2026 | M/S J C ENTERPRISE | 26.65 | 0 | 0 | 75
9 | COOCHBEHAR | Mekliganj | Coochbehar Division | Ground water based Piped Water Supply Scheme DAKSHIN ALOKJHARI MEKHLIGANJ Block | SM/13459 | New | EXECUTION OF DIFFERENT WORK AT SHALBARI ZONE-IIN PWSS |  |  | BILL/02040/2023-2024 | BP-999 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 47.55 | 0 | 0 | 0
10 | COOCHBEHAR | Mekliganj | Northern Mechanical Division II | Ground water based Piped Water Supply Scheme DAKSHIN ALOKJHARI MEKHLIGANJ Block | SM/13459 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of CoochBehar District in West Bengal. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/000063/2025-2026 | 1156/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 488.07 | 0 | 0 | 0
11 | COOCHBEHAR | Mekliganj | Coochbehar Division | Ground water based Piped Water Supply Scheme DAKSHIN ALOKJHARI MEKHLIGANJ Block | SM/13459 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION |  |  | ORD/000049/2025-2026 | 724/CD | 17/05/2025 | 15/08/2025 | AASHIRBAD ENTERPRISE | 83.45 | 0 | 0 | 0
12 | COOCHBEHAR | Mekliganj | Northern Mechanical Division II | Ground water based Piped Water Supply Scheme DAKSHIN ALOKJHARI MEKHLIGANJ Block | SM/13459 | New | Solarization of grid connected pumping installation at Different PWSS at Sitai,Mathabanga and Mekhliganj Block in the dist.of Coochbehar under JJM programme under Northern Mechanical Division-II, PHE Dte | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division,,Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000135/2025-2026 | 1335/NMD-II | 18/06/2025 | 16/09/2025 | M R S ELECTRICAL | 21.84 | 0 | 0 | 0
13 | COOCHBEHAR | Mekliganj | Coochbehar Division | Ground water based Piped Water Supply Scheme DAKSHIN ALOKJHARI MEKHLIGANJ Block | SM/13459 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000291/2025-2026 | 800/CD | 23/05/2025 | 21/08/2025 | MATARA CONSTRUCTION CO. | 34.83 | 0 | 0 | 0
Total | [13 empty] | 20948.56 | 277.01 | 1.32