## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar - II | Coochbehar Division | DHANG DHINGGURI PWSS | SM/13460 | New | Material Requisition To Resource Division |  |  | RTOR000029/2023-2024 | 130/CD | 27/04/2023 |  | Resource Division | 18.63 | 0 | 0 | 0
2 | COOCHBEHAR | Cooch Behar - II | Northern Mechanical Division II | DHANG DHINGGURI PWSS | SM/13460 | New | NEW SERVICE CONNECTION CHARGES AT DHANDHING GURI PWSS PH- I |  |  | BILL/02735/2023-2024 | BP-2023-24-620 | 16/02/2024 |  | WBSEDCL | 5.79 | 0 | 0 | null
3 | COOCHBEHAR | Cooch Behar - II | Northern Mechanical Division II | DHANG DHINGGURI PWSS | SM/13460 | New | NEW SERVICE CONNECTION CHARGES AT DHANDHING GURI PWSS PH- I |  |  | BILL/02735/2023-2024 | BP-2023-24-620 | 16/02/2024 |  | WBSEDCL | 5.79 | 0 | 0 | null
4 | COOCHBEHAR | Cooch Behar - II | Northern Mechanical Division II | DHANG DHINGGURI PWSS | SM/13460 | New | New service connection At Dhandhingguri PH-II |  |  | BILL/02747/2023-2024 | BP-2023-24-637 | 29/02/2024 |  | WBSEDCL | 5.5 | 0 | 0 | null
5 | COOCHBEHAR | Cooch Behar - II | Northern Mechanical Division II | DHANG DHINGGURI PWSS | SM/13460 | New | New service connection At Dhandhingguri PH-II |  |  | BILL/02747/2023-2024 | BP-2023-24-637 | 29/02/2024 |  | WBSEDCL | 5.5 | 0 | 0 | null
6 | COOCHBEHAR | Cooch Behar - II | Coochbehar Division | DHANG DHINGGURI PWSS | SM/13460 | New | Execution of different works related to DHANG DHINGGURI PWSS under JAL JEEVAN MISSION SE NBC1/PHED A. O.: 980/1-5/NBC-1; DT: 19-01-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000460/2022-2023 | 1511/CD | 19/01/2023 | 18/06/2023 | DILIP MAHATO | 369.93 | 233.11 | 63.01 | 53
7 | COOCHBEHAR | Cooch Behar - II | Northern Mechanical Division II | DHANG DHINGGURI PWSS | SM/13460 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for DHANG DHINGGURI water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000841/2023-2024 | 2425/NMD-II | 10/08/2023 | 09/09/2023 | MADHAB SAHA | 18.56 | 5.68 | 30.6 | 50
8 | COOCHBEHAR | Cooch Behar - II | Coochbehar Division | DHANG DHINGGURI PWSS | SM/13460 | New | Execution of different works related to DHANG DHINGGURI PWSS under JAL JEEVAN MISSION |  |  | ORD/000025/2024-2025 | 1133/CD | 14/06/2024 | 13/08/2024 | DILIP MAHATO | 47.6 | 0 | 0 | 0
9 | COOCHBEHAR | Cooch Behar - II | Coochbehar Division | DHANG DHINGGURI PWSS | SM/13460 | New | Execution of different works related to BARAIBARI PWSS under JAL JEEVAN MISSION |  |  | ORD/000087/2024-2025 | 1191/CD | 25/06/2024 | 23/09/2024 | ASHIM KUMAR CHAKRABORTY | 97.02 | 0 | 0 | 0
10 | COOCHBEHAR | Cooch Behar - II | Coochbehar Division | DHANG DHINGGURI PWSS | SM/13460 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
Total | [13 empty] | 20363.61 | 238.79 | 1.17