## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | UTTAR PESHTARJHAR PIPED WATER SUPPLY SCHEME. | SM/13462 | New | Execution of different works related to UTTAR PESHTARJHAR PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1108/1-5/NBC-1; Dt.: 13-02-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000568/2022-2023 | 1688/CD | 13/02/2023 | 18/09/2023 | MS SSB CONSTRUCTION CO | 323.38 | 316.57 | 97.89 | 55
2 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | UTTAR PESHTARJHAR PIPED WATER SUPPLY SCHEME. | SM/13462 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Uttar Peshtarjhar water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000832/2023-2024 | 2410/NMD-II | 10/08/2023 | 09/09/2023 | MADHAB SAHA | 18.48 | 11.26 | 60.91 | 50
3 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | UTTAR PESHTARJHAR PIPED WATER SUPPLY SCHEME. | SM/13462 | New | Execution of different works related to UTTAR PESTARJHAR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000272/2023-2024 | 1040/CD | 22/09/2023 | 21/11/2023 | MS SSB CONSTRUCTION CO | 81.68 | 62.64 | 76.69 | 77
4 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | UTTAR PESHTARJHAR PIPED WATER SUPPLY SCHEME. | SM/13462 | New | Material Requisition To Resource Division |  |  | RTOR000030/2023-2024 | 139/CD | 27/04/2023 | 27/04/2023 | Resource Division | 8.7 | 0 | 0 | 0
5 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | UTTAR PESHTARJHAR PIPED WATER SUPPLY SCHEME. | SM/13462 | New | QUOTATION FOR NSC AT UTTAR PESTERJHAR PH NO I |  |  | BILL/02194/2023-2024 | BP-2023-24-458 | 07/12/2023 | 07/12/2023 | WBSEDCL | 10.49 | 0 | 0 | 0
6 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | UTTAR PESHTARJHAR PIPED WATER SUPPLY SCHEME. | SM/13462 | New | Execution of different works related to UTTAR PESTARJHAR PWSS under JAL JEEVAN MISSION |  |  | ORD/000527/2023-2024 | 323/CD | 09/02/2024 | 09/04/2024 | MS SSB CONSTRUCTION CO | 59.43 | 51.92 | 87.36 | 88
7 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | UTTAR PESHTARJHAR PIPED WATER SUPPLY SCHEME. | SM/13462 | New | NEW SERVICE CONNECTION AT UTTAR PESTARJHAR PWSS, PH-II |  |  | BILL/00840/2024-2025 | BP-250/24-25 | 06/08/2024 | 06/08/2024 | WBSEDCL | 8.42 | 0 | 0 | 0
8 | COOCHBEHAR | Cooch Behar-II | Northern Mechanical Division II | UTTAR PESHTARJHAR PIPED WATER SUPPLY SCHEME. | SM/13462 | New | NEW SERVICE CONNECTION CHARGES FOR PESTARJHAR ZONE-I, PH-I |  |  | BILL/02688/2023-2024 |  | 07/02/2024 | 07/02/2024 | WBSEDCL | 7.36 | 0 | 0 | 0
9 | COOCHBEHAR | Cooch Behar-II | Coochbehar Division | UTTAR PESHTARJHAR PIPED WATER SUPPLY SCHEME. | SM/13462 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION |  |  | ORD/000050/2025-2026 | 705/CD | 17/05/2025 | 15/08/2025 | MS SSB CONSTRUCTION CO | 32.51 | 0 | 0 | 0
Total | [13 empty] | 550.46 | 442.38 | 80.37