## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | BAILPARI PIPED WATER SUPPLY SCHEME. | SM/13463 | New | Material Requisition To Resource Division |  |  | RTOR000078/2023-2024 | 182/CD | 27/04/2023 | 27/04/2023 | Resource Division | 67.88 | 0 | 0 | 0
2 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | BAILPARI PIPED WATER SUPPLY SCHEME. | SM/13463 | New | Execution of different works related to BAILPARI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1338/1-5/NBC-1; Dt.: 24-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000594/2022-2023 | 1964/CD | 24/03/2023 | 21/08/2023 | DILIP MAHATO | 517.09 | 0 | 0 | 85
3 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | BAILPARI PIPED WATER SUPPLY SCHEME. | SM/13463 | New | EXECUTION OF DIFFERENT WORKS RELATED TO (within BAILPARI area) BALASUNDAR PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000605/2024-2025 | 2306/CD | 23/12/2024 | 21/02/2025 | AKANSHA COMMERCIAL PVT. LTD. | 36.65 | 0 | 0 | 0
4 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | BAILPARI PIPED WATER SUPPLY SCHEME. | SM/13463 | New | Execution of different works related to BAILPARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000039/2024-2025 | 1147/CD | 14/06/2024 | 13/08/2024 | DILIP MAHATO | 96.84 | 0 | 0 | 100
5 | COOCHBEHAR | Mathabhanga-II | Coochbehar Division | BAILPARI PIPED WATER SUPPLY SCHEME. | SM/13463 | New | Material Requisition To Resource Division |  |  | RTOR000191/2023-2024 | 86/CD | 11/01/2024 | 11/01/2024 | Resource Division | 12.32 | 0 | 0 | 0
6 | COOCHBEHAR | Mathabhanga-II | Northern Mechanical Division II | BAILPARI PIPED WATER SUPPLY SCHEME. | SM/13463 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BAILPARI TW II. |  |  | BILL/00791/2024-2025 | BP-231/24-25 | 26/07/2024 | 26/07/2024 | WBSEDCL | 13.77 | 0 | 0 | 0
7 | COOCHBEHAR | Mathabhanga-II | Northern Mechanical Division II | BAILPARI PIPED WATER SUPPLY SCHEME. | SM/13463 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT BAILPARI TW I. |  |  | BILL/00792/2024-2025 | BP-232/24-25 | 26/07/2024 | 26/07/2024 | WBSEDCL | 7.79 | 0 | 0 | 0
8 | COOCHBEHAR | Mathabhanga-II | Northern Mechanical Division II | BAILPARI PIPED WATER SUPPLY SCHEME. | SM/13463 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Bailpari Water Supply Scheme TW No.- I AND II under NMD-II,PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/001179/2023-2024 | 2910/NMD-II | 31/10/2023 | 30/11/2023 | SUDIP DUTTA | 18.8 | 0 | 0 | 50
Total | [13 empty] | 771.15 | 0 | 0