## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata - I | Coochbehar Division | KHARIJA BALADANGA PIPED WATER SUPPLY SCHEME | SM/13490 | New | Material Requisition To Resource Division |  |  | RTOR000064/2023-2024 | 173/CD | 27/04/2023 |  | Resource Division | 16.58 | 0 | 0 | 0
2 | COOCHBEHAR | Dinhata - I | Northern Mechanical Division II | KHARIJA BALADANGA PIPED WATER SUPPLY SCHEME | SM/13490 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for KHARIJA BALADANGA water supply scheme, TW no I and II under Northern Mechanical Division-II, PHE Dte.Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 3, Cooch-Behar Mechanical Sub-Division, | ORD/000661/2023-2024 | 1979/NMD-II | 25/07/2023 | 24/08/2023 | M.S ENTERPRISE | 19.46 | 0 | 0 | 0
3 | COOCHBEHAR | Dinhata - I | Northern Mechanical Division II | KHARIJA BALADANGA PIPED WATER SUPPLY SCHEME | SM/13490 | New | QUOTATION FOR NSC AT KHARIJA BABADANGA TW NO II |  |  | BILL/02456/2023-2024 | null | 16/01/2024 |  | WBSEDCL | 3.77 | 0 | 0 | 0
4 | COOCHBEHAR | Dinhata - I | Northern Mechanical Division II | KHARIJA BALADANGA PIPED WATER SUPPLY SCHEME | SM/13490 | New | QUOTATION FOR NSC AT KHARIJA BABADANGA TW NO I |  |  | BILL/02457/2023-2024 | null | 16/01/2024 |  | WBSEDCL | 3.78 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata - I | Northern Mechanical Division II | KHARIJA BALADANGA PIPED WATER SUPPLY SCHEME | SM/13490 | New | New service connection at Kharija baladanga PWSS, P/H-II |  |  | BILL/02319/2023-2024 | BP-2023-24-542 | 17/01/2024 |  | WBSEDCL | 3.77 | 0 | 0 | 0
6 | COOCHBEHAR | Dinhata - I | Northern Mechanical Division II | KHARIJA BALADANGA PIPED WATER SUPPLY SCHEME | SM/13490 | New | New service connection at Kharija baladanga PWSS, P/H-II |  |  | BILL/02319/2023-2024 | BP-2023-24-542 | 17/01/2024 |  | WBSEDCL | 3.77 | 0 | 0 | 0
7 | COOCHBEHAR | Dinhata - I | Coochbehar Division | KHARIJA BALADANGA PIPED WATER SUPPLY SCHEME | SM/13490 | New | Execution of different works related to KHARIJA BALADANGA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000428/2023-2024 | 1484./CD | 20/12/2023 | 18/02/2024 | S.G ENTERPRISE | 87 | 33.72 | 38.76 | 77
8 | COOCHBEHAR | Dinhata - I | Coochbehar Division | KHARIJA BALADANGA PIPED WATER SUPPLY SCHEME | SM/13490 | New | EXECUTION OF DIFFERENT WEORK TA KHARIJA BALADANGA PWSS |  |  | BILL/01994/2023-2024 | BP-1096 | 01/03/2024 |  | S.G ENTERPRISE | 0.93 | 0 | 0 | 0
9 | COOCHBEHAR | Dinhata - I | Northern Mechanical Division II | KHARIJA BALADANGA PIPED WATER SUPPLY SCHEME | SM/13490 | New | New service connection at Kharija Baladanga PWSS, P/H-I. |  |  | BILL/02318/2023-2024 | BP-2023-24-543 | 17/01/2024 |  | WBSEDCL | 3.78 | 0 | 0 | 0
10 | COOCHBEHAR | Dinhata - I | Northern Mechanical Division II | KHARIJA BALADANGA PIPED WATER SUPPLY SCHEME | SM/13490 | New | New service connection at Kharija Baladanga PWSS, P/H-I. |  |  | BILL/02318/2023-2024 | BP-2023-24-543 | 17/01/2024 |  | WBSEDCL | 3.78 | 0 | 0 | 0
11 | COOCHBEHAR | Dinhata - I | Coochbehar Division | KHARIJA BALADANGA PIPED WATER SUPPLY SCHEME | SM/13490 | New | Execution of different works related to KHARIJA BALADANGA PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1002/1-5/NBC-1; Dt.: 24-01-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000484/2022-2023 | 1549/CD | 24/01/2023 | 23/06/2023 | S.G ENTERPRISE | 308.13 | 194.61 | 63.16 | 60
12 | COOCHBEHAR | Dinhata - I | Coochbehar Division | KHARIJA BALADANGA PIPED WATER SUPPLY SCHEME | SM/13490 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
Total | [13 empty] | 20244.05 | 228.33 | 1.13