## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Dinhata-I | Coochbehar Division | KHARIJA BALADANGA PIPED WATER SUPPLY SCHEME | SM/13490 | New | Material Requisition To Resource Division |  |  | RTOR000064/2023-2024 | 173/CD | 27/04/2023 | 27/04/2023 | Resource Division | 16.58 | 0 | 0 | 0
2 | COOCHBEHAR | Dinhata-I | Coochbehar Division | KHARIJA BALADANGA PIPED WATER SUPPLY SCHEME | SM/13490 | New | Execution of different works related to KHARIJA BALADANGA PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1002/1-5/NBC-1; Dt.: 24-01-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION,ASSISTANT ENGINEER, HEAD QUARTER,COOCHBEHAR DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000484/2022-2023 | 1549/CD | 24/01/2023 | 12/02/2025 | S.G ENTERPRISE | 308.13 | 282.39 | 91.65 | 60
3 | COOCHBEHAR | Dinhata-I | Coochbehar Division | KHARIJA BALADANGA PIPED WATER SUPPLY SCHEME | SM/13490 | New | Execution of different works related to KHARIJA BALADANGA PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION | ORD/000428/2023-2024 | 1484./CD | 20/12/2023 | 18/02/2024 | S.G ENTERPRISE | 87 | 67.44 | 77.51 | 77
4 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | KHARIJA BALADANGA PIPED WATER SUPPLY SCHEME | SM/13490 | New | New service connection at Kharija Baladanga PWSS, P/H-I. |  |  | BILL/02318/2023-2024 | BP-2023-24-543 | 17/01/2024 | 17/01/2024 | WBSEDCL | 3.78 | 0 | 0 | 0
5 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | KHARIJA BALADANGA PIPED WATER SUPPLY SCHEME | SM/13490 | New | QUOTATION FOR NSC AT KHARIJA BABADANGA TW NO II |  |  | BILL/02456/2023-2024 |  | 16/01/2024 | 16/01/2024 | WBSEDCL | 3.77 | 0 | 0 | 0
6 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | KHARIJA BALADANGA PIPED WATER SUPPLY SCHEME | SM/13490 | New | QUOTATION FOR NSC AT KHARIJA BABADANGA TW NO I |  |  | BILL/02457/2023-2024 |  | 16/01/2024 | 16/01/2024 | WBSEDCL | 3.78 | 0 | 0 | 0
7 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | KHARIJA BALADANGA PIPED WATER SUPPLY SCHEME | SM/13490 | New | New service connection at Kharija baladanga PWSS, P/H-II |  |  | BILL/02319/2023-2024 | BP-2023-24-542 | 17/01/2024 | 17/01/2024 | WBSEDCL | 3.77 | 0 | 0 | 0
8 | COOCHBEHAR | Dinhata-I | Coochbehar Division | KHARIJA BALADANGA PIPED WATER SUPPLY SCHEME | SM/13490 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
9 | COOCHBEHAR | Dinhata-I | Northern Mechanical Division II | KHARIJA BALADANGA PIPED WATER SUPPLY SCHEME | SM/13490 | New | Implementation of Affordable IoT-Enabled Water Service Delivery Measurement and Monitoring Sensing System for Rural Deployment in the Proposed Villages Under Different Water Supply Schemes at Diferrent Block of CoochBehar District in West Bengal. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division |  | ORD/000063/2025-2026 | 1156/NMD-II | 19/05/2025 | 15/11/2025 | WEBEL TECHNOLOGY LIMITED | 488.07 | 0 | 0 | 0
10 | COOCHBEHAR | Dinhata-I | Coochbehar Division | KHARIJA BALADANGA PIPED WATER SUPPLY SCHEME | SM/13490 | New | EXECUTION OF DIFFERENT WORKS RELATED TO DIFFERENT PWSS UNDER JAL JEEVAN MISSION. |  |  | ORD/000084/2025-2026 | 730/CD | 17/05/2025 | 15/08/2025 | SSPR VALVE MANUFACTURING PVT. LTD. | 96.82 | 0 | 0 | 0
Total | [13 empty] | 20800.99 | 349.83 | 1.68