## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Mekliganj | Coochbehar Division | SHIKARPUR PIPED WATER SUPPLY SCHEME. | SM/13614 | New | Providing FHTC & other allied works at SHIKARPUR PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000387/2022-2023 | 1032/CD | 29/09/2022 | 29/10/2022 | ASHIT KUMAR GHOSH | 9.98 | 0 | 0 | 91
2 | COOCHBEHAR | Mekliganj | Coochbehar Division | SHIKARPUR PIPED WATER SUPPLY SCHEME. | SM/13614 | New | Providing functional house hold tap connection within command area of Shikarpur Piped Water Supply Scheme under Mathabhanga Sub-Division, P.H.E.Dte. Under Jaldhara Programme. | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000155/2022-2023 | 128/MTB | 23/06/2022 | 08/07/2022 | ASIT KR.GHOSH | 4.78 | 4.78 | 100 | 100
3 | COOCHBEHAR | Mekliganj | Northern Mechanical Division II | SHIKARPUR PIPED WATER SUPPLY SCHEME. | SM/13614 | New | QUOTATION FOR NEW SERVICE CONNECTION AT SIKARPUR (AUG PWSS PH NO-II,Z-II |  |  | BILL/00080/2023-2024 | BP-2023-24-73 | 13/05/2023 | 13/05/2023 | WBSEDCL | 1.05 | 0 | 0 | 0
4 | COOCHBEHAR | Mekliganj | Northern Mechanical Division II | SHIKARPUR PIPED WATER SUPPLY SCHEME. | SM/13614 | New | QUOTATION FOR NEW SERVICE CONNECTION AT SIKARPUR (REJU) PWSS PH NO-I,Z-I |  |  | BILL/00079/2023-2024 | BP-2023-24-82 | 15/05/2023 | 15/05/2023 | WBSEDCL | 1.05 | 0 | 0 | 0
5 | COOCHBEHAR | Mekliganj | Northern Mechanical Division II | SHIKARPUR PIPED WATER SUPPLY SCHEME. | SM/13614 | New | QUOTATION FOR NEW SERVICE CONNECTION AT SIKARPUR (AUG PWSS PH NO-I,Z-II |  |  | BILL/00081/2023-2024 | BP-2023-24-72 | 13/05/2023 | 13/05/2023 | WBSEDCL | 1.05 | 0 | 0 | 0
6 | COOCHBEHAR | Mekliganj | Coochbehar Division | SHIKARPUR PIPED WATER SUPPLY SCHEME. | SM/13614 | New | Supply of C.I Specials for SHIKARPUR PWSS(ZONE-I) under JAL JEEVAN MISSION | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000297/2022-2023 | 898/CD | 22/09/2022 | 22/10/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 9.65 | 9.65 | 100 | 1
7 | COOCHBEHAR | Mekliganj | Northern Mechanical Division II | SHIKARPUR PIPED WATER SUPPLY SCHEME. | SM/13614 | New | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT SHIKARPUR (MEKHLIGANJ BLOCK) TW NO. I |  |  | BILL/00750/2024-2025 | BP-211/24-25 | 15/07/2024 | 15/07/2024 | WBSEDCL | 4.61 | 0 | 0 | 0
8 | COOCHBEHAR | Mekliganj | Coochbehar Division | SHIKARPUR PIPED WATER SUPPLY SCHEME. | SM/13614 | New | EXECUTION OF DIFFERENT WORK at SHALBARI ZONE-I PWSS |  |  | BILL/02039/2023-2024 | BP-998 | 03/02/2024 | 03/02/2024 | M/S B PAUL AND COMPANY | 55.7 | 0 | 0 | 0
9 | COOCHBEHAR | Mekliganj | Coochbehar Division | SHIKARPUR PIPED WATER SUPPLY SCHEME. | SM/13614 | New | Execution of different works related to AUG. SIKARPUR PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1287/1-5/NBC-1; Dt.: 17-03-23 | ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION,ASSISTANT ENGINEER, TUFANGANJ SUB-DIVISION | JUNIOR ENGINEER, HEAD QUARTER, COOCH BEHAR DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION,JUNIOR ENGINEER, TUFANGANJ SUB-DIVISION | ORD/000619/2022-2023 | 1905/CD | 17/03/2023 | 14/08/2023 | ASHIM KUMAR CHAKRABORTY | 497.65 | 42 | 8.44 | 40
10 | COOCHBEHAR | Mekliganj | Coochbehar Division | SHIKARPUR PIPED WATER SUPPLY SCHEME. | SM/13614 | New | Execution of different works related to SHIKARPUR PIPED WATER SUPPLY SCHEME. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION,ASSISTANT ENGINEER, RWS COOCHBEHAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000108/2023-2024 | 661/CD | 14/07/2023 | 02/08/2025 | M/S. NITYAGOPAL BANIK | 375.4 | 245.21 | 65.32 | 35
11 | COOCHBEHAR | Mekliganj | Northern Mechanical Division II | SHIKARPUR PIPED WATER SUPPLY SCHEME. | SM/13614 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Shikarpur (Block-Mekhligunj) water supply scheme, TW no I and II under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000852/2023-2024 | 2430/NMD-II | 10/08/2023 | 28/09/2025 | DEB CONSTRUCTION | 22.08 | 0 | 0 | 40
12 | COOCHBEHAR | Mekliganj | Coochbehar Division | SHIKARPUR PIPED WATER SUPPLY SCHEME. | SM/13614 | New | EXECUTION OF DIFFERENT WORKS RELATED TO (within UCHAL PUKHARI ZONE-I, PURBBA DHULIA BALDIHATI & SHIKARPUR area) NIJTARAF PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000593/2024-2025 | 2277/CD | 23/12/2024 | 16/06/2026 | M/S SURAJIT MAJUMDER | 47.03 | 25.25 | 53.69 | 30
Total | [13 empty] | 1030.05 | 326.9 | 31.74