## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar - I | Northern Mechanical Division II | LANKABAR PIPED WATER SUPPLY SCHEME | SM/13618 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Lankabar water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000983/2023-2024 | 2615/NMD-II | 25/08/2023 | 24/09/2023 | M/S PARITOSH BHOWMICK & CO. | 19.76 | 0 | 0 | 0
2 | COOCHBEHAR | Cooch Behar - I | Northern Mechanical Division II | LANKABAR PIPED WATER SUPPLY SCHEME | SM/13618 | New | NEW SERVICE CONNECTION CHARGES AT LANKABAR PWSS, PH - I |  |  | BILL/02736/2023-2024 | BP-2023-24-608 | 16/02/2024 |  | WBSEDCL | 4.89 | 0 | 0 | null
3 | COOCHBEHAR | Cooch Behar - I | Northern Mechanical Division II | LANKABAR PIPED WATER SUPPLY SCHEME | SM/13618 | New | NEW SERVICE CONNECTION CHARGES AT LANKABAR PH-II |  |  | BILL/02740/2023-2024 | BP-2023-24-607 | 16/02/2024 |  | WBSEDCL | 12.94 | 0 | 0 | null
4 | COOCHBEHAR | Cooch Behar - I | Northern Mechanical Division II | LANKABAR PIPED WATER SUPPLY SCHEME | SM/13618 | New | NEW SERVICE CONNECTION CHARGES AT LANKABAR PH-II |  |  | BILL/02740/2023-2024 | BP-2023-24-607 | 16/02/2024 |  | WBSEDCL | 12.94 | 0 | 0 | null
5 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | LANKABAR PIPED WATER SUPPLY SCHEME | SM/13618 | New | Execution of different works related to LANKABAR PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1016/1-5/NBC-1; Dt.: 24-01-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000490/2022-2023 | 1555/CD | 24/01/2023 | 23/06/2023 | NABIN DEBNATH | 251.8 | 30.8 | 12.23 | 25
6 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | LANKABAR PIPED WATER SUPPLY SCHEME | SM/13618 | New | REPARING AND RESTORATION OF DAMAGED FLANK DUE TO PHED PIPE LINE LAYING ALONGSIDEOKRABARI Gobrachara Road road adjacent lonkabar VR ( IN stretches UNDER PWD DINHATA SUB DIVISION UNDER PWD Cooch Behar division in the DISTRICT OF COOCHBEHAR, (1) LANKABAR PIPED WATER SUPPLY SCHEME |  |  | BILL/00360/2024-2025 | null | 20/08/2024 |  | EXECUTIVE ENGINEER PWD COOCHBEHAR DIVISION | 10.13 | 0 | 0 | 0
7 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | LANKABAR PIPED WATER SUPPLY SCHEME | SM/13618 | New | REPARING AND RESTORATION OF DAMAGED FLANK DUE TO PHED PIPE LINE LAYING ALONGSIDE Najirhat NEKIGANJ road VR ( IN stretches UNDER PWD DINHATA SUB DIVISION UNDER PWD Cooch Behar division in the DISTRICT OF COOCHBEHAR |  |  | BILL/00359/2024-2025 | null | 20/08/2024 |  | EXECUTIVE ENGINEER PWD COOCHBEHAR DIVISION | 15.1 | 0 | 0 | 0
Total | [13 empty] | 327.56 | 30.8 | 9.4