## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | PASCHIM MOAMARI PIPED WATER SUPPLY SCHEME | SM/13619 | New | Execution of different works related to PASCHIM MOAMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000359/2023-2024 | 1343/CD | 24/11/2023 | 23/01/2024 | ANIMESH DHAR CHOUDHURY | 86.43 | 0 | 0 | 30
2 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | PASCHIM MOAMARI PIPED WATER SUPPLY SCHEME | SM/13619 | New | Execution of different works related to PASCHIM MOAMARI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1208/1-5/NBC-1; Dt.: 01-03-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000579/2022-2023 | 1769/CD | 02/03/2023 | 30/07/2023 | MATARA CONSTRUCTION CO. | 532.58 | 504.88 | 94.8 | 74
3 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | PASCHIM MOAMARI PIPED WATER SUPPLY SCHEME | SM/13619 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Paschim Moamari water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000987/2023-2024 | 2617/NMD-II | 25/08/2023 | 31/05/2024 | BLUE PINE | 22.1 | 20.81 | 94.15 | 100
4 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | PASCHIM MOAMARI PIPED WATER SUPPLY SCHEME | SM/13619 | New | Material Requisition To Resource Division |  |  | RTOR000146/2023-2024 | 255/CD | 27/04/2023 | 27/04/2023 | Resource Division | 14.75 | 0 | 0 | 0
5 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | PASCHIM MOAMARI PIPED WATER SUPPLY SCHEME | SM/13619 | New | New service connection for PASCHIM MOAMARI PWSS, PH-I |  |  | BILL/02068/2023-2024 | BP-2023-24-432 | 05/12/2023 | 05/12/2023 | WBSEDCL | 5 | 0 | 0 | 0
6 | COOCHBEHAR | Cooch Behar-I | Northern Mechanical Division II | PASCHIM MOAMARI PIPED WATER SUPPLY SCHEME | SM/13619 | New | New service connection for PASCHIM MOAMARI PWSS, PH-II |  |  | BILL/02069/2023-2024 | BP-2023-24-433 | 05/12/2023 | 05/12/2023 | WBSEDCL | 7.04 | 0 | 0 | 0
7 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | PASCHIM MOAMARI PIPED WATER SUPPLY SCHEME | SM/13619 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District(PHALIMARI,SHALBARI,Mansai,SIKARPUR,SAJHERPARGHORAMARA,Nandina,Garbhadanga,BHORAM,FALIMARI,DAKSHINBOKNABANDHA,BHOGRAMGURI,BHERBHERIMANABARI,KHATERBARI,NENDARPAR,NAKARJAN,CHHOTO BOALMARI,PESTARJHAR,CHENGERKUTHIKHALISAMARI,Guriahati,SHUKARURKUTHI,PATCHHARA,DALUA DASGIR,PANIGRAM,CHEKIACHARA, Panisala,BARAIBARI,GHUGHUMARI,JORE SIMULI,BajejamaChilakhanaZI,HEMKUMARIZI,KHARIJAKHAWARDARA,BASRAJAPRATHAMKHANDA,KONACHATRA ZII,AMBARI,SHILGHAGRI,MAHISHKUCHIZII,DHALDIBARI,PHULBARI PB,NAJIRGANJ,MARANADIRKUTHI,NAKKATIGACHHI,BAJRAPUR,GOPALPUR,MAHISHKUCHI ZI,HEMKUMARIZ1PB,KONACHATRAZI,DANGA,DaribashPrathamKhanda,BHALKA, DUAISUAI,BRAHMOTTARCHATRA,Tutiarkuthi, HARINCHAOWRA,CHAKCHAKAZI,Natabari,NAJIRANDEUTIKATA,BARAPHALIMARI,ALOKJHARI,GAJENDRAPUR CHOWRANGEE,NAKKATI,CHIKLIGURI,ANGARKATAPARADUBI,UNISH BASA,KHARIANALDHONDRA,BARARANGRAS,KALARAYERKUTHI, KISMATMOKARARI,JORPATKI,ASAKBARIPRATHAMKHANDA,ABUARPATHAR,DAKSHIN KHARIJAGITALDAHA,INDRANARAYAN,Atpukhari,DHANDHANIA,JNANDAS,JHURIPARA,NUTANBAS,KHARIJADURGANAGARDWITIYAKHANDA,UTTARSINGIMARI,BHUTKURA,BARA ADABARI,CHANDANCHOWRA,PUTIMARIBAKSIBAS,JHINGAPUNI,SAJHERPAR KHATALBARI,KHARIJABALADANGA,DHANGDHINGGURI,SITALKUCHI ZIV, bajejamachilakhanazII,Sitalkuchi ZII,PETLAEPRA,UCHALPUKHARIZI,Chilkirhat,DakshinBasrajbalaZI, SantoshpurZI,BaraSaulmari,SitalkuchiZV,SITALKUCHIZIII,RUIERKHUTHI,BajejamaChilakhana ZIII,SARAHATI,BALASI,MOAMARI,MAINAGURIDIGHALHATI,NIGAMNAGAR,GABUA,DAKSHINALOKJHARI,MARADANGA,PASCHIM MOAMARI,BAISGURIKHANDA,BHULKI,BIJLICHATKA,KHATTIMARIZI,KUCHLIBARIZII,UPENCHAUKIKUCHLIBARI,PutiaBaraMasiaZI,UCHALPUKURIZII,PutiaBaraMasiaZII,BARAKODALIZII,KSHETI,CHHOTAKESHARIBARI,PAKHIHAGA,Kuchlibari ZI,MAHISHCHARU,HEMKUMARI ZII,HEMKUMARI ZIII,DakshinBasrajbalaZII,Takoamari,Sathbhandari,Payamari,MADHYAHUDUMDANGA,SINGIMARIPASCHIMPAR,HARIBHANGA,Bhogmara,LAUCHAPRA,BHANGAMORE,BAROPINJARERJHAR,GHOKSADANGA,DAKSHINBAJEJAMAKHASBAS,JARABARIPRATHAMKHANDA,ANANDARANSINGIMARI underCOB DIV PHED | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 29/10/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 20
8 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | PASCHIM MOAMARI PIPED WATER SUPPLY SCHEME | SM/13619 | New | EXECUTION OF DIFFERENT WORKS RELATED TO TUPAMARI DEWANBAS SHALBARI & PASCHIM MOYAMARI PWSS UNDER JAL JEEVAN MISSION. | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000549/2024-2025 | 2234/CD | 23/12/2024 | 22/04/2025 | MATARA CONSTRUCTION CO. | 51.18 | 2.64 | 5.17 | 30
9 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | PASCHIM MOAMARI PIPED WATER SUPPLY SCHEME | SM/13619 | New | Material Requisition To Resource Division |  |  | RTOR000170/2023-2024 | 71/CD | 11/01/2024 | 11/01/2024 | Resource Division | 14.02 | 0 | 0 | 0
10 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | PASCHIM MOAMARI PIPED WATER SUPPLY SCHEME | SM/13619 | New | REPARING AND RESTORATION OF DAMAGED FLANKCONNECTION TO PHE P LINE LAYING ALONG SIDE Ranirhat road VR adajacent to kismat mokrabari ( IN stretches FROM 0.00 KM TO5.00 KM UNDER MATHABHANGA SUB DIVISION UNDER PWD Cooch Behar division DURING YEAR 2024-2025 |  |  | BILL/00375/2024-2025 |  | 20/08/2024 | 20/08/2024 | EXECUTIVE ENGINEER PWD COOCHBEHAR DIVISION | 15.38 | 0 | 0 | 0
11 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | PASCHIM MOAMARI PIPED WATER SUPPLY SCHEME | SM/13619 | New | REPARING AND RESTORATION OF DAMAGED FLANK DUE TO PHED PIPE LINE LAYING ALONGSIDE DHAPRAMORE TO DHAPRAHAT BAZAR ADJACENT TO PASHIM MOAMARI road VR ( IN stretches UNDER PWD DINHATA SUB DIVISION UNDER PWD Cooch Behar division in the DISTRICT OF COOCHBEHAR, |  |  | BILL/00368/2024-2025 | BP-316 | 31/08/2024 | 31/08/2024 | EXECUTIVE ENGINEER PWD COOCHBEHAR DIVISION | 4.2 | 0 | 0 | 0
12 | COOCHBEHAR | Cooch Behar-I | Coochbehar Division | PASCHIM MOAMARI PIPED WATER SUPPLY SCHEME | SM/13619 | New | REPARING AND RESTORATION OF DAMAGED FLANK DUE TO PHED PIPE LINE LAYING ALONGSIDE ATIABARI FAKIRTAKIA road ADJACENT TO PASCHIM MOYAMARI VR ( IN stretches UNDER PWD DINHATA SUB DIVISION UNDER PWD Cooch Behar division in the DISTRICT OF COOCHBEHA |  |  | BILL/00366/2024-2025 | BP-315 | 31/08/2024 | 31/08/2024 | EXECUTIVE ENGINEER PWD COOCHBEHAR DIVISION | 10.31 | 0 | 0 | 0
Total | [13 empty] | 20552.29 | 528.33 | 2.57