## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | PASCHIM MOAMARI PIPED WATER SUPPLY SCHEME | SM/13619 | New | Material Requisition To Resource Division |  |  | RTOR000146/2023-2024 | 255/CD | 27/04/2023 |  | Resource Division | 14.75 | 0 | 0 | 0
2 | COOCHBEHAR | Cooch Behar - I | Northern Mechanical Division II | PASCHIM MOAMARI PIPED WATER SUPPLY SCHEME | SM/13619 | New | New service connection for PASCHIM MOAMARI PWSS, PH-II |  |  | BILL/02069/2023-2024 | BP-2023-24-433 | 05/12/2023 |  | WBSEDCL | 7.04 | 0 | 0 | 0
3 | COOCHBEHAR | Cooch Behar - I | Northern Mechanical Division II | PASCHIM MOAMARI PIPED WATER SUPPLY SCHEME | SM/13619 | New | New service connection for PASCHIM MOAMARI PWSS, PH-I |  |  | BILL/02068/2023-2024 | BP-2023-24-432 | 05/12/2023 |  | WBSEDCL | 5 | 0 | 0 | 0
4 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | PASCHIM MOAMARI PIPED WATER SUPPLY SCHEME | SM/13619 | New | Execution of different works related to PASCHIM MOAMARI PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION,JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000359/2023-2024 | 1343/CD | 24/11/2023 | 23/01/2024 | ANIMESH DHAR CHOUDHURY | 86.43 | 0 | 0 | 0
5 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | PASCHIM MOAMARI PIPED WATER SUPPLY SCHEME | SM/13619 | New | Material Requisition To Resource Division |  |  | RTOR000170/2023-2024 | 71/CD | 11/01/2024 |  | Resource Division | 14.02 | 0 | 0 | 0
6 | COOCHBEHAR | Cooch Behar - I | Northern Mechanical Division II | PASCHIM MOAMARI PIPED WATER SUPPLY SCHEME | SM/13619 | New | Supply, installation, commissioning and trial operation of electro-mechanical components along with copper wound line voltage corrector for Paschim Moamari water supply scheme, TW no I and II under Jal Jeevan Mission under NMD-II, PHE Dte.APD | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 2, Cooch-Behar Mechanical Sub-Division, | ORD/000987/2023-2024 | 2617/NMD-II | 25/08/2023 | 24/09/2023 | BLUE PINE | 22.1 | 10.4 | 47.08 | 90
7 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | PASCHIM MOAMARI PIPED WATER SUPPLY SCHEME | SM/13619 | New | Execution of different works related to PASCHIM MOAMARI PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1208/1-5/NBC-1; Dt.: 01-03-23 | ASSISTANT ENGINEER, COOCHBEHAR SADAR SUB-DIVISION | JUNIOR ENGINEER, COOCH BEHAR SADAR SUB-DIVISION | ORD/000579/2022-2023 | 1769/CD | 02/03/2023 | 30/07/2023 | MATARA CONSTRUCTION CO. | 532.58 | 373.47 | 70.12 | 74
8 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | PASCHIM MOAMARI PIPED WATER SUPPLY SCHEME | SM/13619 | New | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
9 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | PASCHIM MOAMARI PIPED WATER SUPPLY SCHEME | SM/13619 | New | REPARING AND RESTORATION OF DAMAGED FLANK DUE TO PHED PIPE LINE LAYING ALONGSIDE ATIABARI FAKIRTAKIA road ADJACENT TO PASCHIM MOYAMARI VR ( IN stretches UNDER PWD DINHATA SUB DIVISION UNDER PWD Cooch Behar division in the DISTRICT OF COOCHBEHA |  |  | BILL/00366/2024-2025 | null | 20/08/2024 |  | EXECUTIVE ENGINEER PWD COOCHBEHAR DIVISION | 10.31 | 0 | 0 | 0
10 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | PASCHIM MOAMARI PIPED WATER SUPPLY SCHEME | SM/13619 | New | REPARING AND RESTORATION OF DAMAGED FLANK DUE TO PHED PIPE LINE LAYING ALONGSIDE DHAPRAMORE TO DHAPRAHAT BAZAR ADJACENT TO PASHIM MOAMARI road VR ( IN stretches UNDER PWD DINHATA SUB DIVISION UNDER PWD Cooch Behar division in the DISTRICT OF COOCHBEHAR, |  |  | BILL/00368/2024-2025 | null | 20/08/2024 |  | EXECUTIVE ENGINEER PWD COOCHBEHAR DIVISION | 4.2 | 0 | 0 | 0
11 | COOCHBEHAR | Cooch Behar - I | Coochbehar Division | PASCHIM MOAMARI PIPED WATER SUPPLY SCHEME | SM/13619 | New | REPARING AND RESTORATION OF DAMAGED FLANKCONNECTION TO PHE P LINE LAYING ALONG SIDE Ranirhat road VR adajacent to kismat mokrabari ( IN stretches FROM 0.00 KM TO5.00 KM UNDER MATHABHANGA SUB DIVISION UNDER PWD Cooch Behar division DURING YEAR 2024-2025 |  |  | BILL/00375/2024-2025 | null | 20/08/2024 |  | EXECUTIVE ENGINEER PWD COOCHBEHAR DIVISION | 15.38 | 0 | 0 | 0
Total | [13 empty] | 20501.11 | 383.87 | 1.87