## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-IV TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13684 | Augmentation | Preparation of DPR for Augmentation of SITALKUCHI (Zone-IV) Piped Water Supply Scheme under MATHABHANGA Sub-Division of Cooch Behar Division,P.H.E.Dte. | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000162/2022-2023 | 621/CD | 16/08/2022 | 05/09/2022 | RADIANT | 3.41 | 0 | 0 | 1
2 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-IV TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13684 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000133/2023-2024 | 239/CD | 27/04/2023 |  | Resource Division | 67.01 | 0 | 0 | 0
3 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-IV TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13684 | Augmentation | Providing FHTC Laying of Pipe Line & other allied works at SITALKUCHI ZONE IV PWSS under JAL JEEVAN MISSION | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000504/2022-2023 | 1234/CD. | 28/11/2022 | 28/12/2022 | NORTHE BENGAL CONST CO | 9.91 | 9.91 | 100 | 1
4 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-IV TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13684 | Augmentation | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Augumentation of Sitalkuchi Water Supply Scheme TW No.- I II III and IV of Zone-IV under NMD-II,PHE.Dte,APD. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000806/2023-2024 | 2387/NMD-II | 09/08/2023 | 08/09/2023 | P K ENGINEERING | 41.77 | 0 | 0 | 0
5 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-IV TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13684 | Augmentation | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT SITALKUCHI TW NO. I ZONE-IV |  |  | BILL/02620/2023-2024 | BP-2023-24-582 | 01/02/2024 |  | WBSEDCL | 6.28 | 0 | 0 | null
6 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-IV TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13684 | Augmentation | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT SITALKUCHI TW NO. I ZONE-IV |  |  | BILL/02620/2023-2024 | BP-2023-24-582 | 01/02/2024 |  | WBSEDCL | 6.28 | 0 | 0 | null
7 | COOCHBEHAR |  | Northern Mechanical Division II | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-IV TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13684 | Augmentation | ELECTRIC QUOTATION BILL FOR NEW SERVICE CONNECTION AT SITALKUCHI TW NO. II ZONE-IV |  |  | BILL/02619/2023-2024 | BP-2023-24-583 | 01/02/2024 |  | WBSEDCL | 4.15 | 0 | 0 | null
8 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-IV TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13684 | Augmentation | Laying DI P/Line & other allied works related to STK Z IV PWSS under JAL JEEVAN MISSION |  |  | ORD/000573/2023-2024 | 615/CD | 11/03/2024 | 10/05/2024 | Z STAR COMMOTRADE PVT LTD | 44.77 | 0 | 0 | 0
9 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-IV TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13684 | Augmentation | Laying DI P/Line & other allied works related to STK Z IV PWSS under JAL JEEVAN MISSION |  |  | ORD/000603/2023-2024 | 647/CD | 11/03/2024 | 10/05/2024 | Z STAR COMMOTRADE PVT LTD | 81.72 | 0 | 0 | 0
10 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-IV TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13684 | Augmentation | Execution of different works related to SITALKUCHI Z4 PWSS under JAL JEEVAN MISSION SE,NBC-1,PHED A.O. No.: 1217/1-5/NBC-1; Dt.: 01-03-23 | ASSISTANT ENGINEER, MATHABHANGA SUB-DIVISION | JUNIOR ENGINEER, MATHABHANGA SUB-DIVISION | ORD/000534/2022-2023 | 1779/CD | 02/03/2023 | 30/07/2023 | Z STAR COMMOTRADE PVT LTD | 602.29 | 165.67 | 27.51 | 76
11 | COOCHBEHAR |  | Coochbehar Division | AUGMENTATION OF GROUND WATER BASED SITALKUCHI WATER SUPPLY SCHEME ZONE-IV TO ACCOMMODATE FHTC IN SITALKUCHI BLOCK | SM/13684 | Augmentation | Laying of DI line along both the flanks of Roads in Cooch Behar District under Cooch Behar Division PHE Dte. | CONTRACTUAL ASSISTANT ENGINEER, COOCHBEHAR DIVISION | JUNIOR ENGINEER, RWS COOCH BEHAR SUB-DIVISION | ORD/000339/2024-2025 | 1264/CD | 02/07/2024 | 28/04/2025 | MACKINTOSH BURN LIMITED | 19789.29 | 0 | 0 | 0
Total | [13 empty] | 20656.87 | 175.58 | 0.85